## Executive Office
| EXECUTIVE OFFICE |  |  | 0 | 25 | 50 | 75 | 90 | DONE
ACTIONS | Pre On Site Duties | DONE / STATUS |  | Action to be taken/Date
Apply for the various licenses and permits, set up tracking file
Purchase of Operating Equipment |  | 0 | 0
Stores / Shelving |  | 0 | 0
A) Municipality Building Completion certificate (BCC) to be finalized. | Obtain building completion certificate | 0 | 0
B) Approval and power/water connection. |  | 0 | 0
C) Telecommunication Lines connection |  | 0 | 0
D) SaudiFood Control Authority |  | 0 | 0
E) Civil Defense Inspection & approval. | BCC required, Hotel to take Civil defense through inspection. | 0 | 0
F) Saudii Police Information systems. | BCC required, after which Hotel to obtain approval | 0 | 0
G) CID & Tech License CCTV | Hotel to obtain approval after receiving etisalat lines | 0 | 0
H) Labour law to be implemented | All hotel staff to be on valid work permits | 0 | 0
I) Valid certificate of employee and public liability | Owner to obtain insurance | 0 | 0
G) Saudi Tourism Authority | Saudi Tourism will provide temporary license subject to BCC and | 0 | 0
Developing and controlling pre-opening budget
Prepare and approve an initial working capital budget |  | 0 | 0
Prepare a cash flow in support of the initilal w/c plan |  | 0 | 0
ACCOUNTING, TAX, LEGAL AND BANKING
Appoint and meet auditors |  | 0 | 0
Conduct in-depth briefing with auditors |  | 0 | 0
Initial Meeting with owners re financial information required |  | 0 | 0
Appoint tax agents if applicable | N/A | 0 | 0
Register for VAT/GST and for all other applicable taxes | N/A | 0 | 0
Appoint legal counsel if applicable |  | 0 | 0
Select banker and finalise bank account signatories and obtain resolutions for opening of hotel's |  | 0 | 0
bank account(s). |  | 0 | 0
MEETING WITH GENERAL MANAGER/OWNER
Review status of pre-opening budget |  | 0 | 0
Review status of project, establish opening date |  | 0 | 0
Ensure soft opening date cleared with Owner advised of the date in writing |  | 0 | 0
Owner advised in writing of official opening date |  | 0 | 0
In-house policies and procedures drafted and distributed |  | 0 | 0
INSURANCE |  | 0 | 0
Put in place pre-opening insurance |  | 0 | 0
Put in place all operational insurance |  | 0 | 0
Obtain copies of all insurance policies |  | 0 | 0
FF&E
Confirm with purchasing manager FF&E delivery dates. Ensure staff on site to receive & record |  | 0 | 0
delivery. Storage area to be ready. |  | 0 | 0
OPERATING SUPPLIES |  | 0 | 0
Review physical location of stores to determine adequacy of space (storage and receiving) and |  | 0 | 0
address need for any extra storage space required for temporary storage of initial supplies |  | 0 | 0
Ensure order and delivery dates of hotel's supplies tie in with hotel opening critical plans and that |  | 0 | 0
the order quantities agree with the budget on: |  | 0 | 0
- F&B |  | 0 | 0
- Guest and office supplies |  | 0 | 0
- House supplies |  | 0 | 0
- Operating equipment |  | 0 | 0
Establish procedures to ensure all incoming supplies are maintained in a secure location by the |  | 0 | 0
department head tasked with safeguarding them |  | 0 | 0
FIXED ASSETS
Fixed asset register set up |  | 0 | 0
System acquired to tag and trace all fixed assets |  | 0 | 0
Ensure readines of property to receive fixed assets |  | 0 | 0
Liaise with the auditors on the receiving of the assets |  | 0 | 0
EDP |  | 0 | 0
Review with MIS manager
- Systems configuration |  | 0 | 0
- Location and layout of EDP office and computer room |  | 0 | 0
- Adequacy of alarm systems, fire fighting equipment, aircon, power stabilisers, surge lightning protection system |  | 0 | 0
- Cabling requirements |  | 0 | 0
- Back-up operations and emergency procedures |  | 0 | 0
- Hardware and software agreements |  | 0 | 0
- Adequacy of front office and F&B physical locations |  | 0 | 0
- Layout of stations to allow sufficient space for monitors, printers, cash registers, credit card imprinters, cables, etc |  | 0 | 0
- Provision of special electrical outlets for terminals, etc. |  | 0 | 0
- Develop a systems emergency plan |  | 0 | 0
- Test all systems including the emergency plan |  | 0 | 0
INTER-DEPT, ACCOUNTING RELATED FUNCTIONS
Rooms Department
Obtain details of room structure and configuration, rack rates, discount rates and packaged rates |  | 0 | 0
GDS Connectivity |  | 0 | 0
Expedia/booking.com |  | 0 | 0
Staffing |  | 0 | 0
Housekeeping
Uniforms |  | 0 | 0
Bedlinen |  | 0 | 0
Food & Beverage Department
Opening and closing hours of F&B outlets |  | 0 | 0
Opening and closing hours of F&B stores and policies and procedures for requisitions after hours |  | 0 | 0
Staff entertainment and meal procedures |  | 0 | 0
Coordinate the printing and costing of F&B menus and wine lists |  | 0 | 0
Sales & Marketing
Contracts |  | 0 | 0
Sales and Marketing Plan |  | 0 | 0
Brochures: Meeting Brochures/ Hotel Brochures / Rack Brochures / Fact Sheet |  | 0 | 0
Media Promotion Plan / Press Events ( pre & Post Opening ) |  | 0 | 0
PR & Marketing plan: |  | 0 | 0
Pre Opening press conference |  | 0 | 0
Press Releases |  | 0 | 0
GDS System Build |  | 0 | 0
issue Wholesale contract |  | 0 | 0
Loyalty program |  | 0 | 0
Load Real Live pictures on the WEB |  | 0 | 0
Educational Trips for Corporate / Travel |  | 0 | 0
Participate in RFP's with multinaionals |  | 0 | 0
Incentive Program for corporate bookers |  | 0 | 0
Update Systems with all collaterals of Pre & Post opening |  | 0 | 0
Telephone and Minor Depts
Pricing policies of laundry, valet and business centre etc. |  | 0 | 0
Surcharge on local and long distance calls in line with SCH and local hotel practices |  | 0 | 0
PreOpening Office
Purchase of Operating Equipment |  | 0 | 0
Stores / Shelving |  | 0 | 0
Transportation |  | 0 | 0
Hotel Admin Back Office Furniture |  | 0 | 0
World Clocks/ Sheikhs Portraits |  | 0 | 0
Lead Time |  | 0 | 0
Trial Runs |  | 0 | 0
Soft Opening |  | 0 | 0
DAYS LEFT
SALES & MARKETING
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Handover
Concept Statement
General
Develop Pre-opening budget | GM - OWNER
Develop Annual Budget | DOSM/GM/FC
Order Corporate Program & SOP | GM - OWNER
Organisational Chart | GM/DOSM
Social Economical Outlook | GM
Research on Product Differentiation (USP) | DOSM
Competitive analysis(arthur andersen,etc..) vs. Desired positioning | GM/DOSM/HR
Geographic Segmentation ( GSOB ) | GM/DOSM/HR
Business Segmentation Mix | GM/ DOSM
Decide the Property´s speficic marketing (golf, spa, airport, Resort , City) | DOSM
Develop Sales & Marketing Plan (S&M plan will be a separate document) | DOSM
Define competitive set hotels | DOSM
Define S& M Organization | GM/ DOSM
Schedule sales+ Reservation + Grp Coordination training | DOSM
Hiring process of the S&M Team | DOSM
Sales
Contract Whole Salers | DSOM
Inclusion in Global Preference/Global Access/Corporate programs | DOSM
Contracting DMC programs | DOSM
Contracting Corporate rates | DOSM
Contracting Crew | DOSM/TEAM
Contracting Tour series | DOSM
Update GSO´s with all Collateral Pre and Post Opening . | DOSM/TEAM
Presentatons to GSO Staff | DOSM/TEAM
Outline Educational trips´ calendar with main Accounts | DOSM/TEAM
Outline Educational trips´ calendar with sales / Admn Staff | DOSM/TEAM
Creation of DB - Account base | DOSM
Outline Educational trips´ calendar for reservation staff | DOSM
schedule presentations for agents / Corporate Bookers | DOSM
Create Hotel Manual / Fact Sheet for CRO ´ agents | DOSM
Creative incentive for Corporate Bookers | DOSM
Organize Introductory Corp Conf Call with Cross Divissional Participation | DOSM/ RESV
Inform & Invite taxi drivers companies | DOSM/RESV.
Create Travel & Trade Show Calendar | DOSM/RESV.
Schedule key account events Pre & Post opening | DOSM/RESV.
Develop action plans per segment With S& M Team | DOSM/ HR
Identify Key Accounts | DOSM
Create strategic plan per Key Account | DSOM
Inclusion in Soft Spot marketing programs | DOSM
Implement Rewards programme | DOSM/TEAM
Create Internet promotion in branded websites- | DOSM/TEAM
Create Pre-opening promotion | DOSM
Create daily line-up for Sales teams - Schedule of action prior of exhibitions | DOSM/TEAM
Revenue Management
On- Site PMS configuration | DOSM/REVMN
Configuration on GDS/CRO ( Rates , Inventory etc ) | REVMNGR
Review pricing within GDS/CRO/Internet to ensure consistancy | REVMNGR-DOSM
Create GDS advertising campaign | REVMNGR
Do test reservation in CRO/GDS/Internet | REVMNGR-DOSM
Go live on GDS/CRO/Corporate Web site | REVMNGR
Connect hotel into iHotelier | REVMNGR
Schedule Opera/ TLPC installation & training | DOSM/REVMN
Marketing
Create TOP Accts Mailing List | DOSM
Promotional synergies with local & national tourism and joint activities | DOSM
Check-Registering IHotelier (competitive rate analysis) | DOSM
Research Competitors´ Partner Maketing Programs | DOSM
Research Competitors´list of Associations/ Organisations affiliated | DOSM
Research Competitors´ Own Maketing Programs | DOSM
Explore Partner Marketing opportunities (corporate & local) | DOSM
Define Marketing opportunities with Selected programs (API/FHR) | DOSM
Define Marketing opportunities with Whole Salers | DOSM
Define Marketing opporunities with DMC´s at a Local Level | DOSM/ RESV
Define Marketing opportunities with Local Airlines not included in Corporate deals | DOSM
Define Marketing opportunities with Corporate Companies Local / National Based | DOSM
Define CRM Strategy ( Corporate/ Home made ) See opera Installation dates | DOSM
Order Pricing manual - Awaiting to establish price | DOSM
Develop rate strategy by Segments | DOSM
Submit Hotel Profile/Pricing forms | DOSM
Order Pre-opening manual Reservations Marketing | DOSM
PR
Create PR Plan and Advertising Plan | PR
Schedule press events pre & post opening | PR
Start creation of Press kit and update ongoing | PR
Internal PR for Staff | PR
Diffuse to PR contacts in Feeder markets | PR
Release Editorials | PR
Organise Press Conference Pre-opening | PR
Create Multi Media presentations for press conferences | PR
Organise Press Conference Post-opening | PR
Press trips from Feeder markets | PR
Create Press release | PR
Insertion of Hotel on Corporate Branded websites | PR
Ongoing Updating Pictures and Info on Branded websites. | GM/PR
Include Hotel in Area - Destination websites | PR/DOSM
Install webmail confirmation letter Synaxis | GM/PR
Create pre-opening and post-opening e-brochure (online links, pdfs, emailer) | PR
Inclusion on internet sites (Expedia & local sites) ADTA | PR
Online & Offline Directory Listings
Phone book/Yellow pages inclusion ETISALAT | GM/ HR
Directories: Travel & Tourism Websites and Apps | GM/ HR
F&B and Restaurant Guides
Social Media & Travel Review Sites: Google, FB, TW, TripAdvisor
Whole Salers ( Airtours , V.el Corte Inglés ect ) | DOSM/GM/HR
DMC´s | HR/DOSM
GDS´s | DOSM/HR
Advertising
High Retail Leisure Programs ( AMEX FHR, Virtuoso etc ) | DOSM
Local and Intl Media plan | DOSM
Online & Print: F&B and Restaurants Guides | DOSM
International & Local Magazines and Publications | DOSM
F&B and Restaurant Guides
Define graphic Identity JD | DOSM
Select renderings for preopening collateral / advertising | DOSM
Photography of Mock Up room Subject to Mock up room ready | DOSM
360 / panoramic images - Subject to Mock up rooms ready | DOSM
Collaterals
Load photos on Social Media websites and Travel Apps | DOSM - GM
Create Hotel General Fact Sheet | DOSM
Office Supplies Collateral (letterhead/Business cards) | DOSM
Order insertion in World Wide/ Brand Directories | DOSM
Destination Information + data(photo's, tourist boards, maps) MAP Co. | DOSM
Design all pre-opening + post Opening Collateral JD | PR/DOSM
Pre-opening Powerpoint / Video presentations | GM/DOSM
MICE brochures | DOSM
Rack brochure/Banquet kit/Sales kit,f & b kits | DOSM
Promotional/ Packages collateral brochures | DOSM - GM
obtain copies of all local/competitive collateral | DOSM
DAYS LEFT
TRAINING
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Gather all company information from GM, OM (from start to date) | Property HRD/TC
Gather necessary information for HO and its management team [pictures required] | Property HRD/TC
Begin cross-training activities | Property HRD/TC
Prepare and finalize training manual and materials | Property HRD/TC
Set up Training schedules for Customer Care | Property HRD/TC
Ensure Employee Development Records are prepared per job title | Property HRD/TC
Prepare necessary forms / templates for Training | Property HRD/TC
Ensure Corporate Certificate paper is ordered | Property HRD/TC
Ensure corporate training templates approved by GM, OM | GM
Create standard layout and index for training manuals | Property HRD/TC
Educational and Motivation Frames should be created for GM/OM approval | TC
Frames hanged in approved locations and training room | TC
Ensure that cabinets and storage cupboards for training materials/equipment are ordered and in
place | GM
Check FF&E in accordance with size of training room | TC
Check room layout for furniture placing etc | TC
Ensure safe storage of training equipment | TC
Inventory all training equipment | FC
Source and preview additional training materials and videos | TC
Source and test training equipment | IT Department
Coordinate and develop the departmental shut down [emergency] procedures | Engineering/HR
Coordinate and implement training for hygiene, safety and security | Engineering/HR
Coordinate the Hotel Evacuation with the Chief Engineer | Engineering/HR
Schedule the identified Departmental Trainer to attend the the departmental shut down
procedures training | Engineering/HR
Ensure that Departmental Trainers trains Departmental Shut Down Procedures in their respective
Engineering/HR
departments
Conduct a Fire Training to HODs | Engineering/HR
Implement the Fire Training Manual | Engineering/HR
Finalize fire and evacuation training manual | Engineering/HR
Gather All Departments' information [location, services, etc, timing, etc.] | Property HRD/TC
Plan route and tour guides for employee hotel tours | Property HRD/TC
Ensure that Location Map is in place and in PPT format | Property HRD/TC
Ensure that all HOD's information are updated | Property HRD/TC
Liase with F&B Manager for all Outlets and services information | TC/F&B
Ensure to take photos of pre-opening and opening activities | Property HRD/TC
Coordinate with S&M for company branding | S&M/HRD
Sales and Marketing strategies and other related information | S&M/HRD
Ensure to have all the other hotel services information | S&M/HRD
Scan all HOD's pictures including GM and OM plus Outlet Managers | TC
Take all the perspective of the outlets and other related guest service outlets | TC/F&B
Create training plan / masters in HR & Payroll System | IT Department
Ensure IT Manager assesses Opera/Micros training needs with supplier | IT Department
Ensure IT Manager determines computer training needs prior to opening | IT Department
Ensure IT Manager includes Opera/Micros training sessions into training plans | IT Department
Ensure IT Manager prepares computer master training plan | IT Department
Source out Learning Library Materials with 3 quotations | Property HRD/TC
Identify books required for Library | Property HRD/TC
Identify possible Library Location | Property HRD/TC
Run Hotel BAS's On Job Training Certificate Program for Departmental Trainers | Property HRD/TC
Run Hotel BAS's On Job Training Certificate Program Overview for Department Heads | Property HRD/TC
Schedule an Orientatition Overview for HODS | Property HRD/TC
Ensure training manual is printed for Orientation | Property HRD/TC
Finalise and print delegate materials for General Orientation training | Property HRD/TC
Finalise contents of Orientation training sessions | Property HRD/TC
Finalise schedule for Orientation training | Property HRD/TC
Establish guidelines for lending training materials | Property HRD/TC
Establish system for lending and tracking training equipment | Property HRD/TC
Establish system for storing and maintaining training materials | Property HRD/TC
Establish training equipment maintenance procedure | Property HRD/TC
Implement training for evacuation procedures in Training Department | Property HRD/TC
Implement training for the departmental shut down / Emergency procedures in Training | Property HRD/TC
Set up a system for Communicating training courses/requirements | Property HRD/TC
Set up a system for Cross Exposure | Property HRD/TC
Set up a system for Cross Training | Property HRD/TC
Set Up a system for Departmental Orientation checklists | Property HRD/TC
Set up a system for grooming checks | Property HRD/TC
Set up a system for the completion of Employee Development Records | Property HRD/TC
Set up computer filing system | IT Department
Set up manual filing system | TC
Set up system for Initial Job Training Plans | TC
Coordinate all travel arrangements for pre-opening team | GM/Property HRD
Collect product knowledge quiz questions from departments | TC
Create a question bank for product knowledge quiz | TC
Finalise pre-opening product knowledge quiz schedule | TC
Plan product knowledge quiz programme format | TC
Obtain copies of all departmental Standards of Performance Manuals | TC
Review and finalise the Training Standards of Performance Manual | TC
Finalise and issue the grooming standards for every department | TC
Identify notice board and other opportunities to promote grooming standards | TC
Implement grooming checks | TC
Ensure Standards of Performance Folders are ordered per department | TC
Finalise and order training materials and videos | TC
Order stationery for Training Office | Property HRD/Purchasing
Purchase Frames for Training Room and corridors | Property HRD/Purchasing
Purchase Training Tables and Chairs | Property HRD/Purchasing
Identify Training Committee Members | TC
Hold first Training Committee Meeting | Property HRD/TC
Create Training Manual for Orientation | Property HRD/TC
Identify management training needs | Property HRD/TC
Coordinate / prepare for the approved management training | Property HRD/TC
Coordinate and work with Department Heads to complete the training documentation /
Departmental Training Plan | Property HRD/TC
Create a format for Training Plan | Property HRD/TC
Implement core training plan | Property HRD/TC
Obtain GM's approval on management training plan | GM
Prepare Hotel training calendars in accordance with Mobilisation list | Property HRD/TC
Prepare Hotel training plan in accordance with Legal & Corporate guidelines | Property HRD/TC
Refer to GM for Corporate and Legal training requirements | GM
Refer to GM for external training contractors | GM
Regularly issue core training plan and updates to Department Heads and Departmental Trainers | Property HRD/TC
Review and approve all task breakdowns and on job training plans | Property HRD/TC
Review and finalise departmental skills training plans | Property HRD/TC
Review and finalise management training plan | Property HRD/TC
Weekly review of master training plan and calendar | Property HRD/TC
Evaluate priority training needs for individuals | Property HRD/TC
Establish post-opening training plan based on identified needs | Property HRD/TC
Evaluate priority training needs for Departments | Property HRD/TC
Evaluate priority training needs for Hotel | Property HRD/TC
Outsourced Training Providers should be identified | Property HRD/TC
Identify local and mandatory trainings required for the whole hotel | Property HRD/TC
Ensure that three (3) quotations received for every training training | Property HRD/TC
Coordinate with Outsourced Trainers for details specifications of training required | Property HRD/TC
Ensure to have all the updated KSA information | TC
Ensure Value of the Day is displayed on Training Notice Board | TC
Implement system for communicating value of the day | TC
Issue folders containing laminated Values to all Departments/Outlets | TC
Write and develop the Training Mission | Property HRD/TC
| DAYS LEFT | [20 empty] | 28/09/16
HUMAN RESOURCES
| WORKING DAYS LEFT | [20 empty] | 01/01/17
[5 empty] | WEEK 2: OCT; WEEK 2: NOV; WEEK 2: DEC; WEEK 2: JAN |  |  | FEB |  | APR
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1
Orientation to the Project
Become familiar with Project/Property | Property HRD
Become familiar with Owner/Owning Company | Property HRD
Inventory all HR/Training materials, manuals | Property HRD
Read and become familiar with all materials under HR | Property HRD
Review preliminary manning guide with GM | Property HRD
Identify & Confirm HOD's starting date | Property HRD
Review the pre-opening budget | Property HRD
Review the opening schedule | Property GM
Critical Path
Review the base critical path for the Hotel & HR | Property HRD
Fine tune the base critical path for HR | Property HRD
Upload HR's base critical path into GM's master critical path | Property GM
Establish critical path for Employee Restaurant | Property HRD
Present bi-monthly departmental progress report | Property HRD
Human Resources Office
Finalise office layout and seating | Eng/HK
Finalise F F & E allocation and procurement for HR office | Property HRD
Allocate computer, printers and scanners | IT Department
Order office equipment and supplies | Property HRD
Set up office supplies and stocktaking procedures | Property HRD
Establish HR office equipment inventory | Property HRD
Move into HR offices | Property HRD
Finalise office decoration and posters | Property HRD
Establish office key and key distribution control procedures | Property GM/Property HRD
Set up HR filing system | Property HRD
Establish HR file and cabinet key and key distribution procedures | Property HRD
Finalise installation for computer hardware for HR office | IT Department
Finalise menu for HR office computer files | IT Department
Set up the HR computer system | IT Department
Organisation Structure and Manning
Finalise job titles, candidate profiles, and job descriptions | Property HRD
Prepare preliminary organisation chart with GM for approval | Property HRD/GM
Update the organisation chart for key employees | Property HRD
Issue the completed organisation chart to HOD's | Property HRD
Review staffing guide with respective Department Heads | Property HRD
Finalise hotel staffing guide | Property HRD
Obtain GM's approval for staffing guide | Property HRD
Finalise salary and benefits for each job title with GM | Property HRD
Human Resources Hiring Schedule
Source candidates for HR Secretary | Property HRD
Source candidates HR | Property HRD
Source candidates for Training Manager | Property HRD
HR Secretary begins working | Property HRD
HR staff begins working | Property HRD
Training Manager begins working | Property HRD
Other Purchases
Identify name badge suppplier | Property HRD / Property GM
Order employee name tag from Corporate Supplier | Property HRD / Property GM
Design pre-opening T-shirt | Property GM
Source employee ID card system and ID cards | Property HRD / Property GM
Order employee ID card system and ID cards | Property HRD
Printed Forms and Documents
Put In Place Employee Notification Form | Property HRD
Put In Place Employee Requisition Form | Property HRD
Design Uniform and Equipment Issuance Form | Property HRD
Put In Place Interview Evaluation Worksheet | Property HRD
Design Interview Core Competency Evaluation Worksheet | Property HRD
Put In Place Exit Interview Form | Property HRD
Put In Place Performance Evaluation Form for Line Employees | Property HRD
Put In Place Performance Evaluation Form for Management Personnel | GM/Property HRD
Design Casual Employee Request Form | Property HRD
Put in Place Employee Orientation Checklist | Property HRD
Obtain GM's approval of all printed forms and documents | Property HRD
Print forms and documents | Property HRD
Human Resources Reports
Design a HR Monthly Report template | Property HRD
Put HR Report in place | Property HRD
Standard Correspondence
Implement Application Acknowledgement Letter | Property HRD
Implement Application Referral to Hotel Letter | Property HRD
Design applicationn form | Property HRD
Design New Employee Welcome Letter | Property HRD
Design Confirmation of Employment Letter | Property HRD
Implement Reference Check Letter | Property HRD
Obtain GM's approval of all standard correspondence | Property HRD
General Personnel Administration
Update employee names on the noticeboard | Property HRD
Establish probation trace system through Paytrax | Property HRD
Finalise payroll and related expenses for the pre-opening budget with FC | Property HRD
Track, evaluate and action probations | Property GM/Property HRD
Establish locker room guidelines | Property HRD
Establish and write employee clocking-in procedures | Property HRD
Coordinate the required medical tests for new employees | Property HRD
Coordinate the issuing of locker room keys | Property HRD
Finalise locker room key control procedures | Property HRD
Prepare employee ID cards for incoming employees | Property HRD
Establish procedures with Housekeeping for employee uniform issuing | Property HRD
Schedule employee uniform fittings | Property HRD
Circulate employee uniform fitting schedule | Property HRD
Finalise ID and procedures | Property HRD
Prepare and issue employee ID | Property HRD
Prepare departmental trace system | Property HRD
Prepare employee benefits letters for every employee, by position | Property HRD
Establish medical procedures | Property HRD
Update the list of local HR contacts (emergency services, clinics, etc) | Property HRD
Begin holding daily HR briefings | Property HRD
Set up the manning and payroll reporting systems | Property HRD
Set up the system for tracing and reporting vacations | Property HRD
Set up employee overtime procedures with the Director of Finance | Property HRD
Employee Files
Establish standard format for all employee files | Property HRD
Open employee files for all current employees | Property HRD
Audit employee files for all current employees | Property HRD
Employee Handbook
Develop employee mascot | Property HRD
Complete employee handbook incuding all necessary details | Property HRD
Have Handbook translated into top 5 langauges in property for reference in HR Office | Property HRD
Print employee handbook | Property HRD
Other Employee Collateral
Design contents and components of employee welcome kit for all new employees | Property HRD
Finalise welcome kit for all new employees | Property HRD
Obtain GM's approval of proposed welcome kit | Property HRD
Print and collate employee welcome kits | Property HRD
Issue employee welcome kits | Property HRD
Industrial Relations
Establish guidelines and procedures for employee Sporst & Social committee | Property HRD
Obtain GM's approval for employee Sports & Social committee guidelines | Property HRD
Implement employee Sports & Social committee | Property HRD
Human Resources Policies and Procedures
Establish the template for all departmental policies and procedures | Property HRD
Establish list of required HR policies and procedures | Property HRD
Write the HR policies and procedures | Property HRD
Obtain GM's approval of the HR policies and procedures | Property HRD
Distribute the HR policies and procedures to all Department Heads | Property HRD
Recruitment Advertising
Finalise the format with Marketing for the recruitment advertising campaign | Property HRD
Advertise for local management positions | Property HRD
Advertise for line employees | Property HRD
Recruitment and Selection
Finalise recruitment and job offer procedures | Property HRD
Finalise reference checking procedures | Property HRD
Finalise pre employment medical check procedures | Property HRD
Finalise the hiring schedule with HOD's | Property HRD
Review all candidates on file | Property HRD
File applicants by department and position | Property HRD
Employee Facilities
Review the F F & E for the employee restaurant | Property HRD
Finalise employee restaurant menu schedule | Property HRD
Finalise employee restaurant cleaning schedule | Property HRD
Finalise employee restaurant vending maHotelne programme | Property HRD
Finalise employee restaurant rules and regulations | Property HRD
Finalise employee restaurant opening ceremony | Property HRD
Finalise employee restaurant operating schedule | Property HRD
Open employee restaurant for meals | Property HRD
Hold employee restaurant opening party | Property HRD
Establish employee restaurant committee | Property HRD
Hold a competition to name the employee restaurant | Property HRD
Review F F & E for employee clinic (where appropriate) | Property HRD
Order additional supplies for employee clinic (where appropriate) | Property HRD
Identify nurse and doctor for clinic (where appropriate) | Property HRD
Establish clinic procedures (where appropriate) | Property HRD
Open clinic (where appropriate) | Property HRD
Review F F & E for employee recreation room | Property HRD
Establish employee recreation room procedures | Property HRD
Purchase games, books and other items for employee recreation room | Property HRD
Open employee recreation room | Property HRD
Assign and distribute lockers to employees | Property HRD
Finalise locker control procedures (locker inspections, etc) | Property HRD
Prepare and post hotel grooming standards in locker room | Property HRD
Establish weekly locker walk-about procedure | Property HRD
Decorate the employee entrance area | Property HRD
Decorate the back-of-house areas for employees | Property HRD
Human Resources Employee Services
Set up the employee transportation system | Property HRD
Develop the employee communications schedule (Human Resources calendar) | Property HRD
Check that all departments have noticeboards and are kept updated | Property HRD
Install main employee noticeboards | Property HRD
Finalise content and assignment of main employee noticeboards | Property HRD
Place content on noticeboards | Property HRD
Weekly update of employee noticeboards | Property HRD
Set up system for employee feedback and comments | Property HRD
Monitor departmental communication meetings | Property HRD
Take weekly slides and pictures of pre-opening activities | Property HRD
Take weekly slides and picture of building progress | Property HRD
Employee Recognition Programmes
Post employee recognition posters and distribute collateral to HOD's | Property HRD
Explain programmes guidelines to Department Heads | Property HRD
Make self-nomination forms available for WOW programme | Property HRD
Put in place the forms and procedures for the WOW programme | Property HRD
Install the employee suggestion box for the WOW programme | Property HRD
Establish the gifts that may be redeemed for WOW award points | Property HRD
Make self-nomination forms available for Hotel Champion of the Month programme | Property HRD
Put in place the forms and procedures for the Hotel Champion of the Month
programme | Property HRD
Install the employee suggestion box for the Hotel Champion of the Month
programme | Property HRD
Establish the gifts that may be redeemed for Hotel Champion of the Month award
points | Property HRD
Recognise the Hotel Champion of the Month awards of the quarter | Property HRD
Recognise the Hotel Champion award of the year | Property HRD
Employee Activities
Establish Monthly Team Meeting with employees and GM | Property HRD
Establish committee for pre-opening employee party | Property HRD
Establish guidelines for annual employee party | Property HRD
Establish guidelines for monthly birthday parties | Property GM
Coordinate monthly manager dinners out of hotel (where applicable) | Property HRD
Organise outing for pre-opening support team | Property GM
Organise pre-opening hotel fashion parade party (Uniforms) | Property GM
Human Resources Trial Runs
Coordinate the trial run programme with opening schedule | Property GM
Identify and agree trial run procedures for Rooms | Property GM
Identify and agree trial run procedures for Food and Beverage | Property GM
Publish trial run schedules | Property HRD
Begin trial runs | Property HRD
Assist in monitoring trial runs and feedback sessions | Property HRD
Employee Accommodation (where provided)
Identify and agree location and quantity of employee housing | Property HRD
Establish size, contents and amenities of each unit | Property HRD
Assign units to specific job categories/positions | Property HRD
Agree unit assignment with the GM | Regional Eng./HR
Develop and write policies and procedures for employee housing | Regional Eng./HR
Agree handover schedule for employee housing | Eng/HK
Arrange for post-construction deep cleaning | Regional Eng./HR
Arrange for set-up of units with furniture, linens, etc | Property HRD
Arrange for utilities and other essential services | Property HRD
Arrange for ongoing cleaning and maintenance schedules and manning | ENG/HR
Employees move into accommodation | Property HRD
FOOD & BEVERAGE
[7 empty] | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS
| WEEK 1 |  |  |  | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Administration
Establish Food & Beverage Departmental
Set up F&B Filing System
Set up F&B Tracing System
Review pre opening budget for F&B
Obtain Menus from Competition Hotels
Establish Banquet Pricing / Rental Structures
Review Storerooms for F&B
Establish billing procedures for catering with finance and catering manager
Finalize room rental rates, policies and procedures for banquets
Identify all banquet reports required / set templates and samples
Identify all banquet forms and determine whos scope of work they fall under
Review all back of house offices for F&B
Train Coordinators
Determine banquet & meeting "Actual" seating capacities
Prepare list of business cards for F&B
Establish file system table of contents
Establish pre and post opening meeting schedules
Review Hotel manuals pre opening
Prepare draft rosters for each outlet / full operation
Discuss service sequences for F&B outlets and bars
Discuss uniform design and production for F&B
Property Orientation & walk Through With Restaurant Manager
Concept Design for Menus with Printer
Develop menu items with chef
Menu translation to Arabic
Initial pricing determined
Initial Beverage pricing determined
All menu item costing & use records in place
Kids Menu in place
Beverage list determined, costing & use record in place
All required printed items in place
Final proof read of all menus ( English and Arabic)
All menus go to print
Distribute Menu Proofs for training
Order hours of operation signs for all outlets
All staff on board
F&B trainings, roll plays, practice sessions
Establish procedure for cash bank, key control & tip reporting
Departmental SOPs
Job Description
Restaurant display decorations ordered as necessary
Establish Check order, handling, transfer procedures
Establish silver,china and flatware inventory procedure
Designate Smoking areas for outlets
Plan pre opening beverage order
Place pre opening food store orders
kitchen station assignment set up
Establish Outlet opening and closing procedures
Departmental laundry procedure established
Purchasing
Ordering of FF&E
Order Linen
Initial demand & supply needs of F&B is projected
identify vendors- food, beverage & supplies
Establish order and receiving policies
Reserved signs are in place
Temperature logs in place & documented in audit binder file
Ensure forms food born notification available/in use
Ensure kitchen is clean & Organised to pass Health Inspection
set security and control policy for all stores
set up Inventory & Req system
Issue initial F&B requisitions
Opening & Daily, monthly, quarterly inventory procedures
Set initial par levels food and beverage
Supplies
F&B print order determined
F&B guest and paper supply determined
F&B guest and paper supply vendors determined
proof and print all F&B collateral
Guest check folders ordered
Office supplies and bulletin boards are in place
Set silver, china, flatware par levels
Trainings
Departmental Orientation New Hires (Recurring)
Assess Individual training needs for all hires
Product Knowledge Training (Recurring)
Liase with Human Resources on procedures and budget
Submit list to HR
Develope table of contents for master training manual
Prepare contents for master training manual
Review contents with all key staff
Submit task breakdown sheets to for approval
Implement task breakdown sheets into departmental manual
Schedule departmental training for each outlet
Train Departmental / Divisional Trainers
Family member Core Training
Supervisory Level Core Training
Establish pre- & post opening training schedules
Establish departmental training plan
Draft training strategy for F&B
Shedule a Orientation training
Prepare training calender and schedules
Identify the training location and material needs
Hygiene and sanitation classes
Determine kitchen steward cleaning procedure
Sequence of service training
Train kitchen Team Members, kitchen basics,terminology
Training on telephone techniques
Micros
Confirm location per outlet
Insert all items with supplier
Menu items / name / spec (medium/rare, condiments, etc)
Pricing
output printer kitchen
Payment options ($exchange, credit card, cheque)
Training finished?
Stewarding
Cleaning Strategy SOP
Kitchen night cleaning schedule established
All dish washers are operational and tested
Cleaning procedures
Cleaning control sheets
Chemicals procedures
Opeq storage
Outlet par stocks
CONTRACTS
Beer / beverage / wine / spirits
Plants for public areas with EHK
Coffee / Tea
Night cleaning EHK
Stewarding chemicals
Soft drinks / post mix
Service Training Mock service
Induction Training
F&B Skills Training
Grooming
Micors
Brand Standards
Outlet SOP Training
Floats
Uniforms
Mock Service
Opening Brief
First Requisitions
Snagging and Procedure check
F&B TRIAL RUNS
Prepare schedule for each outlet's trial run
Establish menus (Food & Beverage) for each outlet
Prepare "Guest" comment cards for each outlet
Prepare invitation list with Exco for each outlet
Conduct post mortem of each trial run and give feedback to all
Ensure all costs associated w / trial run are documented
Conduct trial runs
Prepare a trial run questionaire
Prepare a Master Trial Run Schedule
DAYS LEFT
FINANCE
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Contracts, Agreements & Licenses
Obtain copies of Hotel operating management & technical services agreement, and note important
points.
Review executed agreements on expatriate employment, accommodation, etc..
Obtain a copy of the liquor license.
Obtain a copy of the various licenses & permits.
Bank Accounts
Opening operating bank accounts
Finalize authorized signatories
Obtain Cheque books
Appointment of Internal and External auditors (If Required)
Insurance
Appoint of insurance agent for hotel general insurance
Appoint of insurance agent for work men's compensation
Appoint of insurance agent for work men's staff life insurance
Accounting Department's Requirements
Set up Chart of Accounts
Set up Opera transaction codes
Do manual mapping between COA and Opera
Establish format of financial statements, schedules and various reports in line with the Uniform
Systems of Accounts for Hotels
Setup proper internal procedures manual on all accounting matters and distribute to all concerned
Establish policies and procedures for control of keys
Plan for department's various furniture, cabinet and equipment positions on floor plan
Plan for office equipments including computers, fax machines, scanners etc
Forms Design
Finalize the design of various forms for:
All Sales Outlet Checks
Entertainment & Officer's Checks
General Accounting Forms and Reports
Store Requisitions
Operating Inventories & Supplies
Review physical location of stores (General, F&B) to determine adequacy of space (storage &
receiving)
Co-ordinate with Purchasing Manager on Purchase and receiving of operating equipment (ie linen,
silverware, chinaware, glassware, uniform ) and operation supplies
Obtain copies of purchase orders of operating equipments and schedules of delivery and receiving
F&B Inventory
Guest Supplies
Office Supplies
Establish procedures to ensure all incoming stocks (General Store and F&B stores) are received in
permanent storage with details of items received reflected accurately on perpetual records and
other inventory control systems
ACCOUNTING DEPT. RELATED FUNCTIONS
Rooms Department
Policies And Procedures On Complimentary Room Approval
Complimentary Room Amenities Procedures And Accounting For Cost Of Amenities
Obtain Details Of Room Structure And Configuration, Rack Rates, Discount Rates And Packaged
Rates
Food & Beverage Department
Opening And Closing Hours Of F&B Outlets
Opening And Closing Hours Of F&B Stores And Policies And Procedures For Requisition After Office
Hours
Staff Entertainment And Meal Procedures
Co-ordinate The Printing And Costing Of F&B Menus And Wine Lists
Telephone And Minor Operated Depts.
Pricing Policies Of Laundry, Valet Spa and Business Centre
Surcharge Rate On Local And Long Distance Calls In Line
Car-park Fees And Control Procedures
SYSTEMS & INTERNAL CONTROL
Establish Internal Control Procedures With GM And Respective Department Heads And Document
Agreed Procedures For :
Front Office And F&B Departments :
*Front Office Including Concierge
*Front Office Cashiers
*Night Auditor
*Work and Document Flow Generated Through The Front Office To The Accounting Department
*Use Of Cash Registers and Point-Of-Sale Systems
*Guests Checking In And Out Procedures
*Treatment Of Skippers
PURCHASING
Establish Internal Controls For Purchasing, Storage, Receiving And Issuing To Ensure :
*Segregation Of Duties
*Storerooms’ Operating Hours Are Established In Advance and Department Heads Are To Adhere To
*Lead Times On Deliveries are Established to Minimize Inventories
COST CONTROL
Establish Internal Controls For Cost Controller To Ensure :
*Control Of Food Cost
*Control Of Beverage Cost
*Control Minimum & Maximum Stock
*Pricing Of Menus
SOFWARES SET Up
Opera
FBM
SUN / VISION
PAYROLL
MANING
Financial Controller (Expat)
General Cashier/Paymaster (Expat)
Income Auditor (Local)
Accounts Receivable/Payable (Expat)
Cost Controller/ Store In Charge (Expat)
Store Keeper/ Receiving (Local)
Purchasing Manager (Expat)
OFFICE FURNITURE
DAYS LEFT
FRONT OFFICE
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Human Resources
Manning Guide | FOM / DOO
Recruitment Schedule | FOM/ HR
Satff Uniforms Schedule | FOM / EHK
Staff Rostering | FOM
Creating Staff Personal Files | FOM
FF&E & Stocks
FF&E list(Front Office and General Related) | FOM
FF&E Schedule | FOM / Material
Prepare Store Req list per Section | FOM
Prepare Purchase Requests for Sections | FOM
Room Configuration
Room Types and Descriptions | FOM / S&M
Room Numbering | FOM / ENG
Signage | FOM / ENG
Product Knowledge
Services and Timings | FOM/F&B Mgr
Other Dept.Services related to guests | FOM/ Other DH
Food and Beverage Timings | GRO / F&B
Front Office Handbook | GRO / FOM
On-Site Activities | GRO
Update Telephone Book in PMS | Ope / IT
Off-Site Activities & Informations | Concierge / GRO
Reservations
Receives Rate Structure | FOM / S&M
Business on the Books | FOM/Revenue Mgr
Receive Market Segment Manual | S&M
Receive Business Mix Budget | FC
Training on Electronic Procedure & System | FOM / REV
Technical System Configuration
Email Accesses | IT
PMS Set-Up | KIT / IT
GDS-Set-Up | FOM / S&M
Internet Access in Rooms & Public Areas | IT
PABX Set-Up | IT / FOM
Hotel web site set up
Computer/Printer Arrival & Set-Up Deadlines | IT / FOM
Fax Machine & Copier Arrival Deadlines | FOM / Materials
Public Area Tel Booth | IT / FOM
Guest Room Telephones | IT / FOM
Set-Up
Office Lay-Out | FOM / ENG
Reception and Concierge Counter | FOM / ENG
Other Public Areas Responsibilities | FOM / HK
SwitchBoard Lay-Out | FOM
Business Centre Layout | FOM
Telephone Extensions | FOM / Tel Ope
Valet Parking Desk | FOM
Luggage Room | FOM
Training
PMS Classroom Training | FOM / KIT / IT
PMS Workplace Training | FOM / KIT
Hotel Orientation | HR / FOM
Frequent Flyer Training | FOM / S&M
Product Knowledge Training | FOM / Section
Communication Training | FOM / HR
Policy Training | FOM
Procedure SOP Training | FOM
Telephone Standards and Use Training | N Manager
Foreign Currency Training | ACC
Guest Internet Training | IT
Grooming Standards | HR
Guest Safety Deposit Box Training | GRO / ACC
Up Selling Training | FOM
Departmental OJT | HR
Emergency Procedures | ENG
Room Rate and Room code Training | FOM
Market Segment Training | FOM
Reservation Call Sequence Training | FOM
System Shut-Down Training / Contingency Plan | IT / FOM
Accounting
Cash Drop Safe | ACC
Cashier Float Procedure | ACC
General Cashier Procedure | ACC
Lobby/House Phone Procedure | FOM / Tel Ope
Barter Agreement List
Credit List And Procedure | S&M
Collaterals
Corporate In Room Collaterals | S&M
Hotel Defined In Room Printing | HK
Corprate FO Collaterals | FOM
Guest Directory | S&M
Transportation
Taxi Services | FOM
Hotel Shutlle Bus Services | HR / FOM
Hotel Airport Transportation Services | FOM
Policies & Procedures
Prepare & Receive Internal Policies | FOM
Prepare & Receive Internal Procedures SOP,s | FOM
Property Defined FO Services
Difine Business Centre Timings | FOM
Difine Business Centre Services & Prices | FOM
Define Concierge Services & Partner Agents | FOM
Define VIP Amenities | FOM / F&B
DAYS LEFT
HOUSEKEEPING
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Orientation to the Project
Become familiar with Project/Property
Become familiar with Owner/Owning Company
Inventory all HK materials, manuals
Read and become familiar with all materials under HK
Review preliminary manning guide with GM/HR
Review the pre-opening budget
Review the opening schedule
Technical specifications /FF&E Managemnet
Obtain technical specification from contractor/sub contractor
repots) | 2.Upholstery materials ( FR reports)
3.Curtains/Blackouts | ( FR reports)
5.Accessories - Hair dyers/Kettles/bathroom scales/magnify mirrors
FF&E(Asset register)set up
FF&E deliveries/delivery note logs
FF&E hand over by main contractor/FF&E tags /logs
FF&E spares ( furniture)
Critical Path
Review the base critical path for the Hotel & HK
Fine tune the base critical path for HK
Personnel Management
Establish all areas and nos. of manning required/approved GM
candidate profiles/Recruitmnet schedule
Establish Hiring Guide
Departmnetal orientation
Conduct Skills training for all staff
Product knowledge / policy & procedure training lists / test.
Make Training Calender
Make Training Manual
Write Job Descriptions
Draw initial training plan for HK staff & determine who can do training (HR, HK Spvs, Suppliers)
staff on board schedules
Operation Management
Write standards manual (SOP) for total housekeeping & laundry operations
Service procedures
Establish daily routine railroutes with checklists
Make Log Formats
Make Job Allocation Formats
Conduct Time and Motion Study
Purchasing Orders /Par levels
chemicals (check pre-opening budget)
Cleaning material ( SOE)
HK machinery
Trolleys & hangers
Approved & required guest amenities (bathroom & guest room lay out, printing & stationery
Linen orders ( HK / F&B) /Par levels
Guest amenities/stationeries& colleterals/Non wowen items
Implement opening inventories and follow up inventories
Implement bathroom / room set up
Coordination with other departments
Set up standards for future laundry/uniform operations. Collection days/ hours, pick up days/hours for all
Advice other departmnet on Standards & procedures HSK & laundry dept.
Hours & days of pick up clean & delivery of dirty -location for uniforms & linen
Trolleys available for rooms / F&B - locations
Uniforms - approved style on uniforms
Procedures for uniform issue and repairs.
Laundry / Linen Room
Commsion areas to be undertaken for operation for HSK & laundry equip setting up & snagging
Establish all input required for Laundry Micros
Technical control & quality control check lists
Washing machines, dryers, ironing for laundry area before first use. Report defaults
Establish Procedures Delivery & collection of linen
Agree first delivery date of stock in time for training
Linen control
Agree system of linen control with Financial Controller
Implement opening inventories & follow up inventory policy & procedures
Prepare discard linen recycling procedures
Linen arrives on site
Pre-washing of linen
Secure storage and report deviation from standards.
Policy & procedures of issuance, circualtion, misuse control
Uniform schedule
Uniforms - approved style on uniforms
Pre opening T-Shirts
Total manning list for uniforms/ confirm with HOD;s
Produce & issue uniform schedule per dept. (seamstress to be available for small alterations minimum 2 weeks prior to
opening)
Messurment sessions schedule
Fitton schedules and Dilivery
Storage
Linen
Uniforms
Cleaning supplies
Machinery & trolleys
Storage areas policy & procedures
Cleaning materials are on site
Daily follow up of recycled & non-recycled inventory items deliveries
Amenities and HK Supplies
Take out / Stores P&P
Offices and Stores Set Up
HK Offices
Lost and Found Stores
Housekeeping Supplies Store
Chemical Room
Guest Loan Items Store
Equipment Store
Floor Pantry
Linen Store
Uniform Room
Outside Contracts
Finalize: Window cleaning
Plant & Flower suppliers
Outdoor Cleaning
Carpet Maintenance
Marble Maintenance
Make Service procedure outline
Pest Control Hotel
Fragrance contractors
Garbage Procedure
Familiarized w/ garbage collection area & system garbage concept incl. Environmental strategy
Liaise with garbage collection companies
Hygiene & Pest Control
Establish pest control procedures (local contractor)
Request quotations for service agreement to include no. of deep cleans and requested results, call out for vermin
infestations
Handover from Building Contractor
Mock Up room Set up & Review
Receive items from fit out contractor
Snag Mock up room
Hotel Snag Phase I
Hotel Snag Phase II
Take Over final list with snags not completed
Agree handover schedule for rooms and public areas
Arrange for post-construction deep cleaning
Housekeeping Trial Runs
Coordinate the trial run programme with opening schedule
Identify and agree trial run procedures for Rooms
Publish trial run schedules
Begin trial runs
Assist in monitoring trial runs and feedback sessions
DAYS LEFT
PURCHASING
WORKING DAYS LEFT
ACTIONS | ACTION BY |  |  |  | WEEK 3: OCT; WEEK 3: NOV; WEEK 3: DEC; WEEK 3: JAN
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
General
Submit OS&E proposal
Fire Evacuation Plan
LCD Television
Walkie Talkies
Room Safe Boxes
Room Minibar
Hotel Internal Signs
Staff Accommodation Items
Engineering
Engineering Tools
Food & Beverage
Banquet equipments, chinaware, cutleries, glassware and utensils
Wine Bar Equipments
Kitchen Display Items
Kitchen Utensils
Stewarding Items
Housekeeping
Cleaning Equipments
Cleaning Chemicals and Materials
Guest Room Amenities
Room Linen
Bathroom Linen
Guest Room Bed and Mattress
Trolleys for HK
Out door and Indoor Plants contract
Front Office
Flags and Flag Poles 8mtr 12 mtr 5x3 6x4
General
Catering Company
soft drink proposal
Transportations' For Staff
Laundry Service
HACCP Certification TUV SGS BUREAU VERITAS
External cleaning for Building
Outside Catering Van
Fire Retardent Safes
Beverage Contract
Contract for vegetables
Contract for Bread Items
DAYS LEFT
INFORMATION TECHNOLOGY
WORKING DAYS LEFT
ACTIONS | ACTION BY |  |  |  | WEEK 2: OCT; OCT WEEK 2: NOV; NOV WEEK 2: DEC; DEC WEEK 2: JAN
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Installation
Network Cabling to be completed in Data Center
Network Cabling to be completed in in all IDF Rooms
Network Cabling to be completed in all admin Office's
CC TV Project completion and testing
IP Telephone Project completion and testing
HSIA System installation and testing
Apply for telephone lines - Telecommunication
Ordering the Servers , Desktops,Printers, Scanners,etc.,
Applying the Internet line connection from ISP
Data Center to be ready
Opera PMS installation, testing and training for users
Micros POS installation, testing and training for users
HR & PayRoll System installation, testing and training for users
Backoffice System installation ,testing and training for users
Call Accouting System installation and testing
Key Card system installation and testing
All interfaces testing and commissioning
Antivirus system installation and testing
Backup System installation and testing
PC , Scanner and printer distribution in concerned department
Micros Workstation distribution in the Revenue Center
Make sure all the systems and interface are working for the soft opening
Appoint IT Staff's and Training
Soft Opening
DAYS LEFT
ENGINEERING
WORKING DAYS LEFT
[5 empty] | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
ACTIONS | ACTION BY
[5 empty] | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4 | WEEK 1 | WEEK 2 | WEEK 3 | WEEK 4
Set up Engineering files
Complete Emergency Manual
Complete Maintence Manuals / S.O.P.s/ Vol (1) To (5)
Job Descriptions
Complete R&M Budgets
Complete Energy Budget
Fire Plans for Back of Guest Room Doors
Master Key System
Walkie Talkies
Fire Cabinets & Suits for Fire Fighters
Finalise Key Policy
Recruitment
Prepare Snagging List
Prepare Testing & Commissioning Check Lists For M.E.P.
Obtain Quotes For Annual Maintenance Contract
Engineering Tools
Engineering Forms
Finalise Mock Rooms
SAT/TV System
Kitchen Walkin Freezers
General Stores /Shelving
Lobby Reception Desk/set up computer terminals etc
Lobby Café Counter
Take Over Engineering Workshop
Preventative Maintenance Check List/and all work orders
Engineering/Training
Testing Of All M.E.P. Equipment

## Sales & Marketing
SALES AND MARKETING | DAYS LEFT | 95 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 67.8571
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
Handover
Concept Statement |  | 0 | 0 | bar: OCT Wk 1
General
Develop Pre-opening budget | GM - OWNER | 0 | 0 | bar: OCT Wk 1
Develop Annual Budget | DOSM/GM/FC | 0 | 0 | bar: OCT Wk 1
Order Corporate Program & SOP | GM - OWNER |  | 0 | bar: OCT Wk 1
Organisational Chart | GM/DOSM | 0 | 0 | bar: OCT Wk 1
Social Economical Outlook | GM | 0 | 0 | bar: OCT Wk 1
Research on Product Differentiation (USP) | DOSM | 0 | 0 | bar: OCT Wk 1
Competitive analysis(arthur andersen,etc..) vs. Desired positioning | GM/DOSM/HR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Geographic Segmentation ( GSOB ) | GM/DOSM/HR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Business Segmentation Mix | GM/ DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Decide the Property´s speficic marketing (golf, spa, airport, Resort , City) | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Develop Sales & Marketing Plan (S&M plan will be a separate document) | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Define competitive set hotels | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Define S& M Organization | GM/ DOSM | 0 | 0 | bar: OCT Wk 1
Schedule sales+ Reservation + Grp Coordination training | DOSM | 0 | 0 | bar: OCT Wk 4
Hiring process of the S&M Team | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Sales
Contract Whole Salers | DSOM | 0 | 0 | bar: NOV Wk 1
Inclusion in Global Preference/Global Access/Corporate programs | DOSM | 0 | 0 | bar: NOV Wk 1
Contracting DMC programs | DOSM | 0 | 0 | bar: NOV Wk 1
Contracting Corporate rates | DOSM | 0 | 0 | bar: NOV Wk 1
Contracting Crew | DOSM/TEAM | 0 | 0 | bar: NOV Wk 1
Contracting Tour series | DOSM | 0 | 0 | bar: NOV Wk 1
Update GSO´s with all Collateral Pre and Post Opening . | DOSM/TEAM | 0 | 0 | bar: DEC Wk 1
Presentatons to GSO Staff | DOSM/TEAM | 0 | 0
Outline Educational trips´ calendar with main Accounts | DOSM/TEAM | 0 | 0 | bar: DEC Wk 1
Outline Educational trips´ calendar with sales / Admn Staff | DOSM/TEAM | 0 | 0
Creation of DB - Account base | DOSM | 0 | 0 | bar: NOV Wk 1 to NOV Wk 4
Outline Educational trips´ calendar for reservation staff | DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Schedule presentations for agents / Corporate Bookers | DOSM | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Create Hotel Manual / Fact Sheet for CRO ´ agents | DOSM | 0 | 0 | bar: OCT Wk 4
Creative incentive for Corporate Bookers | DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Organize Introductory Corp Conf Call with Cross Divisional Participation | DOSM/ RESV | 0 | 0 | bar: NOV Wk 3
Inform & Invite taxi drivers companies | DOSM/RESV. | 0 | 0 | bar: NOV Wk 4
Create Travel & Trade Show Calendar | DOSM/RESV. | 0 | 0 | bar: OCT Wk 3
Schedule key account events Pre & Post opening | DOSM/RESV. | 0 | 0 | bar: DEC Wk 4
Develop action plans per segment With S& M Team | DOSM/ HR | 0 | 0 | bar: OCT Wk 1
Identify Key Accounts | DOSM | 0 | 0 | bar: OCT Wk 1
Create strategic plan per Key Account | DSOM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Inclusion in Soft Spot marketing programs | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Implement Rewards programme | DOSM/TEAM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Create Internet promotion in branded websites- | DOSM/TEAM | 0 | 0 | bar: DEC Wk 2 to DEC Wk 3
Create Pre-opening promotion | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Create daily line-up for Sales teams - Schedule of action prior of exhibitions | DOSM/TEAM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Revenue Management
On- Site PMS configuration | DOSM/REVMN | 0 | 0 | bar: OCT Wk 4 to NOV Wk 1
Configuration on GDS/CRO ( Rates , Inventory etc ) | REVMNGR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4
Review pricing within GDS/CRO/Internet to ensure consistancy | REVMNGR-DOSM | 0 | 0 | bar: OCT Wk 4
Create GDS advertising campaign | REVMNGR | 0 | 0 | bar: OCT Wk 4
Do test reservation in CRO/GDS/Internet | REVMNGR-DOSM | 0 | 0 | bar: OCT Wk 4; NOV Wk 2
Go live on GDS/CRO/Corporate Web site | REVMNGR | 0 | 0 | bar: NOV Wk 2
Connect hotel into iHotelier | REVMNGR | 0 | 0 | bar: NOV Wk 2
Schedule Opera/ TLPC installation & training | DOSM/REVMN | 0 | 0 | bar: NOV Wk 1
Marketing
Create TOP Accts Mailing List | DOSM | 0 | 0 | bar: NOV Wk 1 to NOV Wk 2
Promotional synergies with local & national tourism and joint activities | DOSM | 0 | 0 | bar: NOV Wk 1 to NOV Wk 3
Check-Registering IHotelier (competitive rate analysis) | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Research Competitors´ Partner Maketing Programs | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Research Competitors´list of Associations/ Organisations affiliated | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Research Competitors´ Own Maketing Programs | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Explore Partner Marketing opportunities (corporate & local) | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define Marketing opportunities with Selected programs (API/FHR) | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define Marketing opportunities with Whole Salers | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define Marketing opporunities with DMC´s at a Local Level | DOSM/ RESV | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define Marketing opportunities with Local Airlines not included in Corporate deals | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define Marketing opportunities with Corporate Companies Local / National Based | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Define CRM Strategy ( Corporate/ Home made ) See opera Installation dates | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Order Pricing manual - Awaiting to establish price | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Develop rate strategy by Segments | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Submit Hotel Profile/Pricing forms | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
Order Pre-opening manual Reservations Marketing | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4
PR
Create PR Plan and Advertising Plan | PR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Schedule press events pre & post opening | PR | 0 | 0 | bar: NOV Wk 3
Start creation of Press kit and update ongoing | PR | 0 | 0 | bar: OCT Wk 4
Internal PR for Staff | PR | 0 | 0 | bar: NOV Wk 3
Diffuse to PR contacts in Feeder markets | PR | 0 | 0 | bar: NOV Wk 1
Release Editorials | PR | 0 | 0 | bar: NOV Wk 1 to NOV Wk 3
Organise Press Conference Pre-opening | PR | 0 | 0 | bar: NOV Wk 2 to NOV Wk 3
Create Multi Media presentations for press conferences | PR | 0 | 0 | bar: OCT Wk 4 to NOV Wk 1
Organise Press Conference Post-opening | PR | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4; DEC Wk 1 to DEC Wk 4
Press trips from Feeder markets | PR | 0 | 0 | bar: DEC Wk 2 to JAN Wk 4
Create Press release | PR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4
Insertion of Hotel on Corporate Branded websites | PR | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4
Ongoing Updating Pictures and Info on Branded websites. | GM/PR | 0 | 0 | bar: NOV Wk 1 to JAN Wk 4
Include Hotel in Area - Destination websites | PR/DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Install webmail confirmation letter Synaxis | GM/PR | 0 | 0 | bar: OCT Wk 1
Create pre-opening and post-opening e-brochure (online links, pdfs, emailer) | PR | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4; DEC Wk 4 to JAN Wk 4
Inclusion on internet sites (Expedia & local sites) ADTA | PR | 0 | 0
Online & Offline Directory Listings
Phone book/Yellow pages inclusion | GM/ HR | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Directories: Travel & Tourism Websites and Apps | GM/ HR | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
F&B and Restaurant Guides |  | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Social Media & Travel Review Sites: Google, FB, TW, TripAdvisor |  | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Whole Salers ( Airtours , V.el Corte Inglés ect ) | DOSM/GM/HR | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
DMC´s | HR/DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
GDS´s | DOSM/HR | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Advertising
High Retail Leisure Programs ( AMEX FHR, Virtuoso etc ) | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
Local and Intl Media plan | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
Online & Print: F&B and Restaurants Guides | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
International & Local Magazines and Publications | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
F&B and Restaurant Guides |  | 0 | 0
Define graphic Identity JD | DOSM | 0 | 0 | bar: OCT Wk 1
Select renderings for preopening collateral / advertising | DOSM | 0 | 0 | bar: OCT Wk 1
Photography of Mock Up room Subject to Mock up room ready | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
360 / panoramic images - Subject to Mock up rooms ready | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 2
Advertising
Load photos on Social Media websites and Travel Apps | DOSM - GM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4; DEC Wk 4 to JAN Wk 4
Create Hotel General Fact Sheet | DOSM | 0 | 0 | bar: OCT Wk 2 to OCT Wk 4; DEC Wk 4 to JAN Wk 4
Office Supplies Collateral (letterhead/Business cards) | DOSM | 0 | 0 | bar: NOV Wk 3 to NOV Wk 4
Order insertion in World Wide/ Brand Directories | DOSM | 0 | 0 | bar: OCT Wk 3 to NOV Wk 1
Destination Information + data(photo's, tourist boards, maps) MAP Co. | DOSM | 0 | 0 | bar: NOV Wk 3 to NOV Wk 4
Design all pre-opening + post Opening Collateral JD | PR/DOSM | 0 | 0
Pre-opening Powerpoint / Video presentations | GM/DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
MICE brochures | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4
Rack brochure/Banquet kit/Sales kit,f & b kits | DOSM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
Promotional/ Packages collateral brochures | DOSM - GM | 0 | 0 | bar: NOV Wk 4 to DEC Wk 1
obtain copies of all local/competitive collateral | DOSM | 0 | 0 | bar: OCT Wk 1 to OCT Wk 4

## Training
TRAINING | DAYS LEFT | 95 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 67.8571
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4 | Wk 1 | Wk 2 | Wk 3 | Wk 4
General
Gather all company information from GM, FC & CE (from start to date) | HRD/TC | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
Gather necessary information for HO and its management team [pictures required] | HRD/TC | 0 | 0 | bar: OCT Wk 2 to OCT Wk 3
Begin cross-training activities | HRD/TC | 0 | 0 | bar: DEC Wk 1
Prepare and finalize training manual and materials | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Set up Training schedules for Customer Care | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Ensure Employee Development Records are prepared per job title | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Prepare necessary forms / templates for Training | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Ensure Corporate Certificate paper is ordered | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Ensure corporate training templates approved by GM, OM | GM | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Create standard layout and index for training manuals | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Educational and Motivation Frames should be created for GM/OM approval | TC | 0 | 0
Frames hanged in approved locations and training room | TC | 0 | 0 | bar: NOV Wk 1
Ensure that cabinets and storage cupboards for training materials/equipment are ordered and in |  | 0 | 0 | bar: NOV Wk 1
place | GM | 0 | 0 | bar: NOV Wk 1
Check FF&E in accordance with size of training room | TC | 0 | 0 | bar: NOV Wk 1
Check room layout for furniture placing etc | TC | 0 | 0 | bar: NOV Wk 1
Ensure safe storage of training equipment | TC | 0 | 0
Inventory all training equipment | FC | 0 | 0
Source and preview additional training materials and videos | TC | 0 | 0
Source and test training equipment | IT Department | 0 | 0
Coordinate and develop the departmental shut down [emergency] procedures | Engineering/HR | 0 | 0
Coordinate and implement training for hygiene, safety and security | Engineering/HR | 0 | 0
Coordinate the Hotel Evacuation with the Chief Engineer | Engineering/HR | 0 | 0
Schedule the identified Departmental Trainer to attend the the departmental shut down |  | 0 | 0
procedures training | Engineering/HR | 0 | 0
Ensure that Departmental Trainers trains Departmental Shut Down Procedures in their respective |  | 0 | 0
departments | Engineering/HR | 0 | 0
Conduct a Fire Training to HODs | Engineering/HR | 0 | 0
Implement the Fire Training Manual | Engineering/HR | 0 | 0 | bar: NOV Wk 1
Finalize fire and evacuation training manual | Engineering/HR | 0 | 0 | bar: NOV Wk 1
Gather All Departments' information [location, services, etc, timing, etc.] | HRD/TC | 0 | 0 | bar: OCT Wk 3
Plan route and tour guides for employee hotel tours | HRD/TC | 0 | 0 | bar: OCT Wk 3
Ensure that Location Map is in place and in PPT format | HRD/TC | 0 | 0
Ensure that all HOD's information are updated | HRD/TC | 0 | 0
Liase with F&B Manager for all Outlets and services information | TC/F&B | 0 | 0
Ensure to take photos of pre-opening and opening activities | HRD/TC | 0 | 0
Coordinate with S&M for company branding | S&M/HRD | 0 | 0
Sales and Marketing strategies and other related information | S&M/HRD | 0 | 0
Ensure to have all the other hotel services information | S&M/HRD | 0 | 0
Scan all HOD's pictures including GM and OM plus Outlet Managers | TC | 0 | 0
Take all the perspective of the outlets and other related guest service outlets | TC/F&B | 0 | 0
Create training plan / masters in HR & Payroll System | IT Department | 0 | 0
Ensure IT Manager assesses Opera/Micros training needs with supplier | IT Department | 0 | 0
Ensure IT Manager determines computer training needs prior to opening | IT Department | 0 | 0
Ensure IT Manager includes Opera/Micros training sessions into training plans | IT Department | 0 | 0
Ensure IT Manager prepares computer master training plan | IT Department | 0 | 0
Source out Learning Library Materials with 3 quotations | HRD/TC | 0 | 0
Identify books required for Library | HRD/TC | 0 | 0
Identify possible Library Location | HRD/TC | 0 | 0
Run Hotel BAS's On Job Training Certificate Program for Departmental Trainers | HRD/TC | 0 | 0 | bar: NOV Wk 1 to NOV Wk 4
Run Hotel BAS's On Job Training Certificate Program Overview for Department Heads | HRD/TC | 0 | 0 | bar: NOV Wk 1 to NOV Wk 4
Schedule an Orientatition Overview for HODS | HRD/TC | 0 | 0
Ensure training manual is printed for Orientation | HRD/TC | 0 | 0 | bar: NOV Wk 1
Finalise and print delegate materials for General Orientation training | HRD/TC | 0 | 0
Finalise contents of Orientation training sessions | HRD/TC | 0 | 0
Finalise schedule for Orientation training | HRD/TC | 0 | 0
Establish guidelines for lending training materials | HRD/TC | 0 | 0
Establish system for lending and tracking training equipment | HRD/TC | 0 | 0
Establish system for storing and maintaining training materials | HRD/TC | 0 | 0
Establish training equipment maintenance procedure | HRD/TC | 0 | 0
Implement training for evacuation procedures in Training Department | HRD/TC | 0 | 0
Implement training for the departmental shut down / Emergency procedures in Training | HRD/TC | 0 | 0
Set up a system for Communicating training courses/requirements | HRD/TC | 0 | 0
Set up a system for Cross Exposure | HRD/TC | 0 | 0
Set up a system for Cross Training | HRD/TC | 0 | 0
Set Up a system for Departmental Orientation checklists | HRD/TC | 0 | 0
Set up a system for grooming checks | HRD/TC | 0 | 0
Set up a system for the completion of Employee Development Records | HRD/TC | 0 | 0
Set up computer filing system | IT Department | 0 | 0
Set up manual filing system | TC | 0 | 0
Set up system for Initial Job Training Plans | TC | 0 | 0
Coordinate all travel arrangements for pre-opening team | GM/HRD | 0 | 0
Collect product knowledge quiz questions from departments | TC | 0 | 0
Create a question bank for product knowledge quiz | TC | 0 | 0
Finalise pre-opening product knowledge quiz schedule | TC | 0 | 0
Plan product knowledge quiz programme format | TC | 0 | 0
Obtain copies of all departmental Standards of Performance Manuals | TC | 0 | 0
Review and finalise the Training Standards of Performance Manual | TC | 0 | 0
Finalise and issue the grooming standards for every department | TC | 0 | 0
Identify notice board and other opportunities to promote grooming standards | TC | 0 | 0
Implement grooming checks | TC | 0 | 0
Ensure Standards of Performance Folders are ordered per department | TC | 0 | 0
Finalise and order training materials and videos | TC | 0 | 0
Order stationery for Training Office | HRD/Purchasing | 0 | 0
Purchase Frames for Training Room and corridors | HRD/Purchasing | 0 | 0
Purchase Training Tables and Chairs | HRD/Purchasing | 0 | 0
Identify Training Committee Members | TC | 0 | 0
Hold first Training Committee Meeting | HRD/TC | 0 | 0 | bar: DEC Wk 1 to DEC Wk 2
Create Training Manual for Orientation | HRD/TC | 0 | 0
Identify management training needs | HRD/TC | 0 | 0
Coordinate / prepare for the approved management training | HRD/TC | 0 | 0
Coordinate and work with Department Heads to complete the training documentation / | HRD/TC | 0 | 0
Departmental Training Plan | HRD/TC | 0 | 0
Create a format for Training Plan | HRD/TC | 0 | 0
Implement core training plan | HRD/TC | 0 | 0
Obtain GM's approval on management training plan | GM | 0 | 0
Prepare Hotel training calendars in accordance with Mobilisation list | HRD/TC | 0 | 0
Prepare Hotel training plan in accordance with Legal & Corporate guidelines | HRD/TC | 0 | 0
Refer to GM for Corporate and Legal training requirements | GM | 0 | 0
Refer to GM for external training contractors | GM | 0 | 0
Regularly issue core training plan and updates to Department Heads and Departmental Trainers | HRD/TC | 0 | 0
Review and approve all task breakdowns and on job training plans | HRD/TC | 0 | 0
Review and finalise departmental skills training plans | HRD/TC | 0 | 0
Review and finalise management training plan | HRD/TC | 0 | 0
Weekly review of master training plan and calendar | HRD/TC | 0 | 0
Evaluate priority training needs for individuals | HRD/TC | 0 | 0
Establish post-opening training plan based on identified needs | HRD/TC | 0 | 0
Evaluate priority training needs for Departments | HRD/TC | 0 | 0
Evaluate priority training needs for Hotel | HRD/TC | 0 | 0
Outsourced Training Providers should be identified | HRD/TC | 0 | 0
Identify local and mandatory trainings required for the whole hotel | HRD/TC | 0 | 0
Ensure that three (3) quotations received for every training training | HRD/TC | 0 | 0
Coordinate with Outsourced Trainers for details specifications of training required | HRD/TC | 0 | 0
Ensure to have all the updated KSA information | TC | 0 | 0
Ensure Value of the Day is displayed on Training Notice Board | TC | 0 | 0
Implement system for communicating value of the day | TC | 0 | 0
Issue folders containing laminated Values to all Departments/Outlets | TC | 0 | 0
Write and develop the Training Mission | HRD/TC | 0 | 0

## Human Resources
HUMAN RESOURCES | DAYS LEFT | 95 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 67.8571
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Orientation to the Project
Become familiar with Project/Property | HRD | 0 | 0 | bar: OCT WK 2
Become familiar with Owner/Owning Company | HRD | 0 | 0 | bar: OCT WK 2
Inventory all HR/Training materials, manuals | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Read and become familiar with all materials under HR | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Review preliminary manning guide with GM | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Identify & Confirm HOD's starting date | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Review the pre-opening budget | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Review the opening schedule | GM | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Critical Path
Review the base critical path for the Hotel & HR | HRD | 0 | 0 | bar: OCT WK 2
Fine tune the base critical path for HR | HRD | 0 | 0 | bar: OCT WK 4
Upload HR's base critical path into GM's master critical path | GM | 0 | 0 | bar: OCT WK 4
Establish critical path for Employee Restaurant | HRD | 0 | 0 | bar: OCT WK 4
Present weekly departmental progress report | HRD | 0 | 0 | bar: NOV WK 1
Human Resources Office
Finalise office layout and seating | Eng/HK | 0 | 0 | bar: OCT WK 4
Finalise F F & E allocation and procurement for HR office | HRD | 0 | 0 | bar: OCT WK 4
Allocate computer, printers and scanners | IT Department | 0 | 0 | bar: OCT WK 4
Order office equipment and supplies | HRD | 0 | 0 | bar: OCT WK 4
Set up office supplies and stocktaking procedures | HRD | 0 | 0 | bar: OCT WK 4
Establish HR office equipment inventory | HRD | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Move into HR offices | HRD | 0 | 0 | bar: OCT WK 4
Finalise office decoration and posters | HRD | 0 | 0 | bar: OCT WK 4
Establish office key and key distribution control procedures | GM / HRD | 0 | 0 | bar: OCT WK 4
Set up HR filing system | HRD | 0 | 0 | bar: NOV WK 1
Establish HR file and cabinet key and key distribution procedures | HRD | 0 | 0 | bar: NOV WK 1
Finalise installation for computer hardware for HR office | IT Department | 0 | 0 | bar: NOV WK 1
Finalise menu for HR office computer files | IT Department | 0 | 0 | bar: NOV WK 1
Set up the HR computer system | IT Department | 0 | 0 | bar: NOV WK 1
Organisation Structure and Manning
Finalise job titles, candidate profiles, and job descriptions | HRD | 0 | 0 | bar: OCT WK 4
Prepare preliminary organisation chart with GM for approval | HRD / GM | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Update the organisation chart for key employees | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Issue the completed organisation chart to HOD's | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Review staffing guide with respective Department Heads | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Finalise hotel staffing guide | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Obtain GM's approval for staffing guide | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Finalise salary and benefits for each job title with GM | HRD | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Human Resources Hiring Schedule
Source candidates for HR Secretary/NA | HRD | 0 | 0 | bar: OCT WK 2
Source candidates HR | HRD | 0 | 0 | bar: OCT WK 2
Source candidates for Training Manager | HRD | 0 | 0 | bar: DEC WK 1
HR Secretary begins working | HRD | 0 | 0 | bar: NOV WK 1
HR staff begins working | HRD | 0 | 0 | bar: NOV WK 1
Training Manager begins working | HRD | 0 | 0 | bar: DEC WK 4
Other Purchases
Identify name badge suppplier | HRD / GM | 0 | 0 | bar: OCT WK 2
Order employee name tag from Corporate Supplier | HRD / GM | 0 | 0 | bar: OCT WK 3
Design pre-opening T-shirt | GM | 0 | 0 | bar: OCT WK 3
Source employee ID card system and ID cards | HRD / GM | 0 | 0 | bar: OCT WK 3
Order employee ID card system and ID cards | HRD | 0 | 0 | bar: OCT WK 3
Printed Forms and Documents
Put In Place Employee Notification Form | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Put In Place Employee Requisition Form | HRD | 0 | 0 | bar: OCT WK 3
Design Uniform and Equipment Issuance Form | HRD | 0 | 0 | bar: OCT WK 3
Put In Place Interview Evaluation Worksheet | HRD | 0 | 0 | bar: OCT WK 3
Design Interview Core Competency Evaluation Worksheet | HRD | 0 | 0 | bar: OCT WK 3
Put In Place Exit Interview Form | HRD | 0 | 0 | bar: OCT WK 3
Put In Place Performance Evaluation Form for Line Employees | HRD | 0 | 0 | bar: OCT WK 3 to DEC WK 4
Put In Place Performance Evaluation Form for Management Personnel | HRD / GM | 0 | 0 | bar: OCT WK 3 to DEC WK 4
Design Casual Employee Request Form | HRD | 0 | 0 | bar: OCT WK 3
Put in Place Employee Orientation Checklist | HRD | 0 | 0 | bar: OCT WK 3
Obtain GM's approval of all printed forms and documents | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Print forms and documents | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Human Resources Reports
Design a HR Monthly Report template | HRD | 0 | 0 | bar: OCT WK 4 to NOV WK 4
Put HR Report in place | HRD | 0 | 0 | bar: NOV WK 1 to DEC WK 1
Standard Correspondence
Implement Application Acknowledgement Letter | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Implement Application Referral to Hotel Letter | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Design applicationn form | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Design New Employee Welcome Letter | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Design Confirmation of Employment Letter | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Implement Reference Check Letter | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Obtain GM's approval of all standard correspondence | HRD | 0 | 0 | bar: OCT WK 3 to OCT WK 4
General Personnel Administration
Update employee names on the noticeboard | HRD | 0 | 0 | bar: NOV WK 1
Establish probation trace system through Paytrax | HRD | 0 | 0 | bar: NOV WK 1
Finalise payroll and related expenses for the pre-opening budget with FC | HRD | 0 | 0
Track, evaluate and action probations | GM / HRD | 0 | 0 | bar: NOV WK 1
Establish locker room guidelines | HRD | 0 | 0 | bar: NOV WK 1
Establish and write employee clocking-in procedures | HRD | 0 | 0 | bar: NOV WK 1
Coordinate the required medical tests for new employees | HRD | 0 | 0
Coordinate the issuing of locker room keys | HRD | 0 | 0 | bar: NOV WK 1
Finalise locker room key control procedures | HRD | 0 | 0 | bar: NOV WK 1
Prepare employee ID cards for incoming employees | HRD | 0 | 0 | bar: NOV WK 1
Establish procedures with Housekeeping for employee uniform issuing | HRD | 0 | 0 | bar: NOV WK 1
Schedule employee uniform fittings | HRD | 0 | 0 | bar: NOV WK 1
Circulate employee uniform fitting schedule | HRD | 0 | 0 | bar: NOV WK 2
Finalise ID and procedures | HRD | 0 | 0 | bar: NOV WK 2
Prepare and issue employee ID | HRD | 0 | 0 | bar: NOV WK 2
Prepare departmental trace system | HRD | 0 | 0 | bar: NOV WK 3
Prepare employee benefits letters for every employee, by position | HRD | 0 | 0 | bar: NOV WK 3
Establish medical procedures | HRD | 0 | 0 | bar: NOV WK 3
Update the list of local HR contacts (emergency services, clinics, etc) | HRD | 0 | 0 | bar: NOV WK 3
Begin holding daily HR briefings | HRD | 0 | 0 | bar: NOV WK 1
Set up the manning and payroll reporting systems | HRD | 0 | 0 | bar: NOV WK 1
Set up the system for tracing and reporting vacations | HRD | 0 | 0 | bar: DEC WK 3
Set up employee overtime procedures with the Director of Finance | HRD | 0 | 0 | bar: JAN WK 1
Employee Files
Establish standard format for all employee files | HRD | 0 | 0 | bar: NOV WK 1
Open employee files for all current employees | HRD | 0 | 0 | bar: NOV WK 1
Audit employee files for all current employees | HRD | 0 | 0 | bar: NOV WK 1
Employee Handbook
Develop employee mascot | HRD | 0 | 0 | bar: NOV WK 1
Complete employee handbook incuding all necessary details | HRD | 0 | 0 | bar: NOV WK 1
Have Handbook translated into top 5 langauges in property for reference in HR Office | HRD | 0 | 0 | bar: NOV WK 2
Print employee handbook | HRD | 0 | 0 | bar: NOV WK 2
Other Employee Collateral
Design contents and components of employee welcome kit for all new employees | HRD | 0 | 0 | bar: OCT WK 3
Finalise welcome kit for all new employees | HRD | 0 | 0 | bar: OCT WK 3
Obtain GM's approval of proposed welcome kit | HRD | 0 | 0 | bar: OCT WK 3
Print and collate employee welcome kits | HRD | 0 | 0 | bar: OCT WK 4
Issue employee welcome kits | HRD | 0 | 0 | bar: OCT WK 4
Industrial Relations
Establish guidelines and procedures for employee Sporst & Social committee | HRD | 0 | 0 | bar: JAN WK 3
Obtain GM's approval for employee Sports & Social committee guidelines | HRD | 0 | 0 | bar: JAN WK 4
Implement employee Sports & Social committee | HRD | 0 | 0 | bar: JAN WK 4
Human Resources Policies and Procedures
Establish the template for all departmental policies and procedures | HRD | 0 | 0 | bar: JAN WK 1
Establish list of required HR policies and procedures | HRD | 0 | 0 | bar: JAN WK 1
Write the HR policies and procedures | HRD | 0 | 0 | bar: JAN WK 2
Obtain GM's approval of the HR policies and procedures | HRD | 0 | 0 | bar: JAN WK 2
Distribute the HR policies and procedures to all Department Heads | HRD | 0 | 0 | bar: JAN WK 3
Recruitment Advertising
Finalise the format with Marketing for the recruitment advertising campaign | HRD | 0 | 0 | bar: OCT WK 2
Advertise for local management positions | HRD | 0 | 0 | bar: OCT WK 2
Advertise for line employees | HRD | 0 | 0 | bar: NOV WK 1
Recruitment and Selection
Finalise recruitment and job offer procedures | HRD | 0 | 0 | bar: OCT WK 3
Finalise reference checking procedures | HRD | 0 | 0 | bar: OCT WK 4
Finalise pre employment medical check procedures | HRD | 0 | 0 | bar: OCT WK 4
Finalise the hiring schedule with HOD's | HRD | 0 | 0 | bar: OCT WK 1
Review all candidates on file | HRD | 0 | 0 | bar: OCT WK 1
File applicants by department and position | HRD | 0 | 0 | bar: OCT WK 2
Employee Facilities
Review the F F & E for the employee restaurant | HRD | 0 | 0 | bar: OCT WK 2
Finalise employee restaurant menu schedule | HRD | 0 | 0 | bar: OCT WK 3
Finalise employee restaurant cleaning schedule | HRD | 0 | 0 | bar: NOV WK 1
Finalise employee restaurant vending program | HRD | 0 | 0 | bar: NOV WK 1
Finalise employee restaurant rules and regulations | HRD | 0 | 0 | bar: NOV WK 1
Finalise employee restaurant opening ceremony | HRD | 0 | 0 | bar: NOV WK 1
Finalise employee restaurant operating schedule | HRD | 0 | 0 | bar: NOV WK 1
Open employee restaurant for meals | HRD | 0 | 0 | bar: NOV WK 1
Hold employee restaurant opening party | HRD | 0 | 0 | bar: NOV WK 1
Establish employee restaurant committee | HRD | 0 | 0 | bar: NOV WK 2
Hold a competition to name the employee restaurant | HRD | 0 | 0 | bar: NOV WK 2
Review F F & E for employee clinic (where appropriate) | HRD | 0 | 0 | bar: NOV WK 1
Order additional supplies for employee clinic (where appropriate) | HRD | 0 | 0 | bar: NOV WK 1
Identify nurse and doctor for clinic (where appropriate) | HRD | 0 | 0 | bar: NOV WK 1
Establish clinic procedures (where appropriate) | HRD | 0 | 0 | bar: NOV WK 1
Open clinic (where appropriate) | HRD | 0 | 0 | bar: DEC WK 1
Review F F & E for employee recreation room | HRD | 0 | 0 | bar: DEC WK 1
Establish employee recreation room procedures | HRD | 0 | 0 | bar: DEC WK 1
Purchase games, books and other items for employee recreation room | HRD | 0 | 0 | bar: DEC WK 1
Open employee recreation room | HRD | 0 | 0 | bar: JAN WK 1
Assign and distribute lockers to employees | HRD | 0 | 0 | bar: DEC WK 1
Finalise locker control procedures (locker inspections, etc) | HRD | 0 | 0 | bar: DEC WK 1
Prepare and post hotel grooming standards in locker room | HRD | 0 | 0 | bar: DEC WK 1
Establish weekly locker walk-about procedure | HRD | 0 | 0 | bar: DEC WK 1
Decorate the employee entrance area | HRD | 0 | 0 | bar: DEC WK 1
Decorate the back-of-house areas for employees | HRD | 0 | 0 | bar: DEC WK 2
Human Resources Employee Services
Set up the employee transportation system | HRD | 0 | 0 | bar: OCT WK 4
Develop the employee communications schedule (Human Resources calendar) | HRD | 0 | 0 | bar: NOV WK 1
Check that all departments have noticeboards and are kept updated | HRD | 0 | 0 | bar: NOV WK 1
Install main employee noticeboards | HRD | 0 | 0 | bar: NOV WK 2
Finalise content and assignment of main employee noticeboards | HRD | 0 | 0 | bar: NOV WK 2
Place content on noticeboards | HRD | 0 | 0 | bar: NOV WK 2
Weekly update of employee noticeboards | HRD | 0 | 0 | bar: NOV WK 2
Set up system for employee feedback and comments | HRD | 0 | 0 | bar: DEC WK 1
Monitor departmental communication meetings | HRD | 0 | 0 | bar: DEC WK 1
Take weekly slides and pictures of pre-opening activities | HRD | 0 | 0 | bar: OCT WK 4
Take weekly slides and picture of building progress | HRD | 0 | 0 | bar: OCT WK 4 to DEC WK 4
Employee Recognition Programs
Post employee recognition posters and distribute collateral to HOD's | HRD | 0 | 0 | bar: JAN WK 4
Explain programmes guidelines to Department Heads | HRD | 0 | 0 | bar: JAN WK 4
Make self-nomination forms available for WOW programme | HRD | 0 | 0 | bar: JAN WK 4
Put in place the forms and procedures for the WOW programme | HRD | 0 | 0 | bar: JAN WK 4
Install the employee suggestion box for the WOW programme | HRD | 0 | 0 | bar: JAN WK 4
Establish the gifts that may be redeemed for WOW award points | HRD | 0 | 0 | bar: JAN WK 4
Make self-nomination forms available for Hotel Champion of the Month programme | HRD | 0 | 0 | bar: JAN WK 4
Put in place the forms and procedures for the Hotel Champion of the Month Program | HRD | 0 | 0 | bar: JAN WK 4
Install the employee suggestion box for the Hotel Champion of the Month programme | HRD | 0 | 0 | bar: JAN WK 4
Establish the gifts that may be redeemed for Hotel Champion of the Month award points | HRD | 0 | 0 | bar: JAN WK 4
Recognise the Hotel Champion of the Month awards of the quarter | HRD | 0 | 0 | bar: JAN WK 4
Recognise the Hotel Champion award of the year | HRD | 0 | 0 | bar: JAN WK 4
Employee Activities
Establish Monthly Team Meeting with employees and GM | HRD | 0 | 0 | bar: OCT WK 4
Establish committee for pre-opening employee party | HRD | 0 | 0 | bar: DEC WK 3
Establish guidelines for annual employee party | HRD | 0 | 0 | bar: JAN WK 1
Establish guidelines for monthly birthday parties | GM | 0 | 0 | bar: JAN WK 3
Coordinate monthly manager dinners out of hotel (where applicable) | HRD | 0 | 0 | bar: JAN WK 2
Organise outing for pre-opening support team | GM | 0 | 0 | bar: DEC WK 3
Organise pre-opening hotel fashion parade party (Uniforms) | GM | 0 | 0 | bar: DEC WK 2
Human Resources Trial Runs
Coordinate the trial run programme with opening schedule | GM | 0 | 0 | bar: DEC WK 1
Identify and agree trial run procedures for Rooms | GM | 0 | 0 | bar: DEC WK 1
Identify and agree trial run procedures for Food and Beverage | GM | 0 | 0 | bar: DEC WK 1
Publish trial run schedules | HRD | 0 | 0 | bar: DEC WK 2
Begin trial runs | HRD | 0 | 0 | bar: DEC WK 2
Assist in monitoring trial runs and feedback sessions | HRD | 0 | 0 | bar: DEC WK 2
Employee Accommodation (where provided)
Identify and agree location and quantity of employee housing | HRD | 0 | 0 | bar: OCT WK 3
Establish size, contents and amenities of each unit | HRD | 0 | 0 | bar: OCT WK 3
Assign units to specific job categories/positions | HRD | 0 | 0 | bar: OCT WK 3
Agree unit assignment with the GM | Regional Eng./HR | 0 | 0 | bar: OCT WK 3
Develop and write policies and procedures for employee housing | Regional Eng./HR | 0 | 0 | bar: OCT WK 3
Agree handover schedule for employee housing | Eng/HK | 0 | 0 | bar: OCT WK 3
Arrange for post-construction deep cleaning | Regional Eng./HR | 0 | 0 | bar: OCT WK 3
Arrange for set-up of units with furniture, linens, etc | HRD | 0 | 0 | bar: OCT WK 3
Arrange for utilities and other essential services | HRD | 0 | 0 | bar: OCT WK 3
Arrange for ongoing cleaning and maintenance schedules and manning | ENG/HR | 0 | 0 | bar: OCT WK 3
Employees move into accommodation | HRD | 0 | 0 | bar: OCT WK 3

## Food & Beverage
FOOD & BEVERAGE | DAYS LEFT | 95 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 67.8571
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Administration
Establish Food & Beverage Departmental |  | 0 | 0 | bar: DEC WK 1
Set up F&B Filing System |  | 0 | 0 | bar: DEC WK 1
Set up F&B Tracing System |  | 0 | 0 | bar: DEC WK 1
Review pre opening budget for F&B |  | 0 | 0 | bar: DEC WK 3
Obtain Menus from Competition Hotels |  | 0 | 0 | bar: OCT WK 4
Establish Banquet Pricing / Rental Structures |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Review Storerooms for F&B |  | 0 | 0 | bar: NOV WK 2
Establish billing procedures for catering with finance and catering manager |  | 0 | 0 | bar: NOV WK 1
Finalize room rental rates, policies and procedures for banquets |  | 0 | 0 | bar: NOV WK 1
Identify all banquet reports required / set templates and samples |  | 0 | 0 | bar: OCT WK 4
Identify all banquet forms and determine whos scope of work they fall under |  | 0 | 0 | bar: OCT WK 4
Review all back of house offices for F&B |  | 0 | 0 | bar: OCT WK 4
Train Coordinators |  | 0 | 0 | bar: NOV WK 1
Determine banquet & meeting "Actual" seating capacities |  | 0 | 0 | bar: NOV WK 2
Prepare list of business cards for F&B |  | 0 | 0 | bar: NOV WK 3
Establish file system table of contents |  | 0 | 0 | bar: NOV WK 4
Establish pre and post opening meeting schedules |  | 0 | 0 | bar: DEC WK 1
Review Hotel manuals pre opening |  | 0 | 0
Prepare draft rosters for each outlet / full operation |  | 0 | 0
Discuss service sequences for F&B outlets and bars |  | 0 | 0 | bar: DEC WK 2
Discuss uniform design and production for F&B |  | 0 | 0 | bar: DEC WK 1
Property Orientation & walk Through With Restaurant Manager |  | 0 | 0 | bar: DEC WK 1
Concept Design for Menus with Printer |  | 0 | 0 | bar: DEC WK 1
Develop menu items with chef |  | 0 | 0 | bar: NOV WK 2
Menu translation to Arabic |  | 0 | 0 | bar: NOV WK 3
Initial pricing determined |  | 0 | 0 | bar: NOV WK 4
Initial Beverage pricing determined |  | 0 | 0 | bar: NOV WK 4
All menu item costing & use records in place |  | 0 | 0 | bar: NOV WK 1
Kids Menu in place |  | 0 | 0 | bar: NOV WK 3
Beverage list determined, costing & use record in place |  | 0 | 0 | bar: NOV WK 1
All required printed items in place |  | 0 | 0 | bar: DEC WK 2
Final proof read of all menus ( English and Arabic) |  | 0 | 0 | bar: DEC WK 1
All menus go to print |  | 0 | 0 | bar: DEC WK 2
Distribute Menu Proofs for training |  | 0 | 0
Order hours of operation signs for all outlets |  | 0 | 0 | bar: DEC WK 1
All staff on board |  | 0 | 0 | bar: NOV WK 1
F&B trainings, roll plays, practice sessions |  | 0 | 0 | bar: NOV WK 2
Establish procedure for cash bank, key control & tip reporting |  | 0 | 0 | bar: NOV WK 4
Departmental SOPs |  | 0 | 0 | bar: NOV WK 1
Job Description |  | 0 | 0 | bar: NOV WK 1
Restaurant display decorations ordered as necessary |  | 0 | 0 | bar: NOV WK 2
Establish Check order, handling, transfer procedures |  | 0 | 0 | bar: NOV WK 2
Establish silver,china and flatware inventory procedure |  | 0 | 0 | bar: NOV WK 2
Designate Smoking areas for outlets |  | 0 | 0 | bar: NOV WK 2
Plan pre opening beverage order |  | 0 | 0 | bar: DEC WK 1
Place pre opening food store orders |  | 0 | 0 | bar: DEC WK 1
kitchen station assignment set up |  | 0 | 0 | bar: DEC WK 1
Establish Outlet opening and closing procedures |  | 0 | 0 | bar: DEC WK 1
Departmental laundry procedure established |  | 0 | 0 | bar: DEC WK 1
Purchasing
Ordering of FF&E |  | 0 | 0 | bar: NOV WK 1
Order Linen |  | 0 | 0 | bar: NOV WK 1
Initial demand & supply needs of F&B is projected |  | 0 | 0 | bar: NOV WK 1
Identify vendors- food, beverage & supplies |  | 0 | 0 | bar: NOV WK 1
Establish order and receiving policies |  | 0 | 0 | bar: NOV WK 1
Reserved signs are in place |  | 0 | 0 | bar: NOV WK 2
Temperature logs in place & documented in audit binder file |  | 0 | 0 | bar: NOV WK 2
Ensure forms food born notification available/in use |  | 0 | 0 | bar: NOV WK 2
Ensure kitchen is clean & Organised to pass Health Inspection |  | 0 | 0 | bar: NOV WK 2
Set security and control policy for all stores |  | 0 | 0 | bar: NOV WK 2
Set up Inventory & Req system |  | 0 | 0 | bar: NOV WK 2
Issue initial F&B requisitions |  | 0 | 0 | bar: NOV WK 2
Opening & Daily, monthly, quarterly inventory procedures |  | 0 | 0 | bar: NOV WK 2
Set initial par levels food and beverage |  | 0 | 0 | bar: NOV WK 2
Supplies
F&B print order determined |  | 0 | 0 | bar: NOV WK 1
F&B guest and paper supply determined |  | 0 | 0 | bar: NOV WK 1
F&B guest and paper supply vendors determined |  | 0 | 0 | bar: NOV WK 1
proof and print all F&B collateral |  | 0 | 0 | bar: NOV WK 1
Guest check folders ordered |  | 0 | 0 | bar: NOV WK 1
Office supplies and bulletin boards are in place |  | 0 | 0 | bar: NOV WK 1
Set silver, china, flatware par levels |  | 0 | 0 | bar: NOV WK 1
Trainings
Departmental Orientation New Hires (Recurring) |  | 0 | 0 | bar: DEC WK 1
Assess Individual training needs for all hires |  | 0 | 0 | bar: DEC WK 1
Product Knowledge Training (Recurring) |  | 0 | 0 | bar: DEC WK 1
Liase with Human Resources on procedures and budget |  | 0 | 0 | bar: DEC WK 1
Submit list to HR |  | 0 | 0 | bar: DEC WK 1
Develope table of contents for master training manual |  | 0 | 0 | bar: DEC WK 1
Prepare contents for master training manual |  | 0 | 0 | bar: DEC WK 1
Review contents with all key staff |  | 0 | 0 | bar: DEC WK 1
Submit task breakdown sheets to for approval |  | 0 | 0 | bar: DEC WK 1
Implement task breakdown sheets into departmental manual |  | 0 | 0 | bar: DEC WK 1
Schedule departmental training for each outlet |  | 0 | 0 | bar: DEC WK 1
Train Departmental / Divisional Trainers |  | 0 | 0 | bar: DEC WK 1
Family member Core Training |  | 0 | 0 | bar: DEC WK 1
Supervisory Level Core Training |  | 0 | 0 | bar: DEC WK 1
Establish pre- & post opening training schedules |  | 0 | 0 | bar: DEC WK 1
Establish departmental training plan |  | 0 | 0 | bar: DEC WK 1
Draft training strategy for F&B |  | 0 | 0 | bar: DEC WK 1
Shedule a Orientation training |  | 0 | 0 | bar: DEC WK 1
Prepare training calender and schedules |  | 0 | 0 | bar: DEC WK 1
Identify the training location and material needs |  | 0 | 0 | bar: DEC WK 1
Hygiene and sanitation classes |  | 0 | 0 | bar: DEC WK 1
Determine kitchen steward cleaning procedure |  | 0 | 0 | bar: DEC WK 1
Sequence of service training |  | 0 | 0 | bar: DEC WK 1
Train kitchen Team Members, kitchen basics,terminology |  | 0 | 0 | bar: DEC WK 1
Training on telephone techniques |  | 0 | 0 | bar: DEC WK 1
Micros
Confirm location per outlet |  | 0 | 0 | bar: DEC WK 2
Insert all items with supplier |  | 0 | 0 | bar: DEC WK 2
Menu items / name / spec (medium/rare, condiments, etc) |  | 0 | 0 | bar: DEC WK 2
Pricing |  | 0 | 0 | bar: DEC WK 2
Output printer kitchen |  | 0 | 0 | bar: DEC WK 2
Payment options ($exchange, credit card, cheque) |  | 0 | 0 | bar: DEC WK 2
Training finished? |  | 0 | 0 | bar: DEC WK 2
Stewarding
Cleaning Strategy SOP |  | 0 | 0 | bar: NOV WK 3
Kitchen night cleaning schedule established |  | 0 | 0 | bar: NOV WK 3
All dish washers are operational and tested |  | 0 | 0 | bar: NOV WK 3
Cleaning procedures |  | 0 | 0 | bar: NOV WK 3
Cleaning control sheets |  | 0 | 0 | bar: NOV WK 3
Chemicals procedures |  | 0 | 0 | bar: NOV WK 3
Opeq storage |  | 0 | 0 | bar: NOV WK 3
Outlet par stocks |  | 0 | 0 | bar: NOV WK 3
CONTRACTS
Beer / beverage / wine / spirits |  | 0 | 0 | bar: DEC WK 2
Plants for public areas with EHK |  | 0 | 0 | bar: DEC WK 2
Coffee / Tea |  | 0 | 0 | bar: DEC WK 2
Night cleaning EHK |  | 0 | 0 | bar: DEC WK 2
Stewarding chemicals |  | 0 | 0 | bar: DEC WK 2
Soft drinks / post mix |  | 0 | 0 | bar: DEC WK 2
Service Training Mock service
Induction Training |  | 0 | 0 | bar: DEC WK 2
F&B Skills Training |  | 0 | 0 | bar: DEC WK 2
Grooming |  | 0 | 0 | bar: DEC WK 2
Micors |  | 0 | 0 | bar: DEC WK 2
Brand Standards |  | 0 | 0 | bar: DEC WK 2
Outlet SOP Training |  | 0 | 0 | bar: DEC WK 2
Floats |  | 0 | 0 | bar: DEC WK 2
Uniforms |  | 0 | 0 | bar: DEC WK 2
Mock Service |  | 0 | 0 | bar: DEC WK 2
Opening Brief |  | 0 | 0 | bar: DEC WK 2
First Requisitions |  | 0 | 0 | bar: DEC WK 2
Snagging and Procedure check |  | 0 | 0 | bar: DEC WK 2
F&B TRIAL RUNS
Prepare schedule for each outlet's trial run |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Establish menus (Food & Beverage) for each outlet |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Prepare "Guest" comment cards for each outlet |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Prepare invitation list with Exco for each outlet |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Conduct post mortem of each trial run and give feedback to all |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Ensure all costs associated w / trial run are documented |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Conduct trial runs |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Prepare a trial run questionaire |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Prepare a Master Trial Run Schedule |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4

## Finance
ACCOUNTING | DAYS LEFT | 95 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 67.8571
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
General
Obtain copies of Hotel operating management & technical services agreement, and note important points. | FC | 0 | 0 | bar: OCT WK 2 to OCT WK 3
Review executed agreements on expatriate employment, accommodation, etc.. |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Obtain a copy of the liquor license. | FC | 0 | 0 | bar: DEC WK 2
Obtain a copy of the various licenses & permits. |  | 0 | 0 | bar: DEC WK 2
Bank Accounts
Opening operating bank accounts |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Finalize authorized signatories |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Obtain Cheque books |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Appointment of Internal and External auditors (If Required) | FC | 0 | 0 | bar: NOV WK 4
Insurance
Appoint of insurance agent for hotel general insurance |  | 0 | 0 | bar: NOV WK 4
Appoint of insurance agent for work men's compensation | FC | 0 | 0 | bar: NOV WK 4
Appoint of insurance agent for work men's staff life insurance | FC | 0 | 0 | bar: NOV WK 4
Accounting Department's Requirements
Set up Chart of Accounts |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Set up Opera transaction codes |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Do manual mapping between COA and Opera |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Establish format of financial statements, schedules and various reports in line with the Uniform Systems of Accounts for Hotels |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Setup proper internal procedures manual on all accounting matters and distribute to all concerned |  | 0 | 0 | bar: NOV WK 4
Establish policies and procedures for control of keys |  | 0 | 0 | bar: NOV WK 4
Plan for department's various furniture, cabinet and equipment positions on floor plan |  | 0 | 0 | bar: OCT WK 2
Plan for office equipments including computers, fax machines, scanners etc |  | 0 | 0 | bar: OCT WK 2
Forms Design
Finalize the design of various forms for: |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
All Sales Outlet Checks |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Entertainment & Officer's Checks |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
General Accounting Forms and Reports |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Store Requisitions |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Operating Inventories & Supplies
Review physical location of stores (General, F&B) to determine adequacy of space (storage & receiving) |  | 0 | 0 | bar: OCT WK 3
Co-ordinate with Purchasing Manager on Purchase and receiving of operating equipment (ie linen, silverware, chinaware, glassware, uniform ) and operation supplies |  | 0 | 0 | bar: OCT WK 2
Obtain copies of purchase orders of operating equipments and schedules of delivery and receiving |  | 0 | 0 | bar: OCT WK 2
F&B Inventory ¦ Guest Supplies ¦ Office Supplies
Establish procedures to ensure all incoming stocks (General Store and F&B stores) are received in permanent storage with details of items received reflected accurately on perpetual records and other inventory control systems |  | 0 | 0 | bar: NOV WK 1
ACCOUNTING DEPT. RELATED FUNCTIONS
Rooms Department
Policies and procedures on complimentary room approval |  | 0 | 0 | bar: NOV WK 3
Complimentary room amenities procedures and accounting for cost of amenities |  | 0 | 0 | bar: NOV WK 3
Obtain details of room structure and configuration, rack rates, discount rates and packaged rates |  | 0 | 0 | bar: NOV WK 3
Food & Beverage Department
Opening and closing hours of F&B outlets |  | 0 | 0 | bar: NOV WK 1
Opening and closing hours of F&B stores and policies and procedures for requisition after office hours |  | 0 | 0 | bar: NOV WK 1
Staff Entertainment And Meal Procedures |  | 0 | 0 | bar: NOV WK 1
Co-ordinate The Printing And Costing Of F&B Menus And Wine Lists |  | 0 | 0 | bar: OCT WK 3
Telephone And Minor Operated Depts.
Pricing Policies Of Laundry, Valet Spa and Business Centre |  | 0 | 0 | bar: NOV WK 1
Surcharge Rate On Local And Long Distance Calls In Line |  | 0 | 0 | bar: NOV WK 1
Car-park Fees And Control Procedures |  | 0 | 0 | bar: NOV WK 1
SYSTEMS & INTERNAL CONTROL
Establish internal control procedures with GM and respective HODs and document agreed procedures for :
Front Office And F&B Departments :
- Front Office Including Concierge |  | 0 | 0 | bar: NOV WK 4
- Front Office Cashiers |  | 0 | 0 | bar: NOV WK 4
- Night Auditor |  | 0 | 0 | bar: NOV WK 4
- Work and Document Flow Generated Through The Front Office To The Accounting Department |  | 0 | 0 | bar: NOV WK 4
- Use Of Cash Registers and Point-Of-Sale Systems |  | 0 | 0 | bar: NOV WK 4
- Guests Checking In And Out Procedures |  | 0 | 0 | bar: NOV WK 4
- Treatment Of Skippers |  | 0 | 0 | bar: NOV WK 4
PURCHASING
Establish internal controls for purchasing, storage, receiving and issuing to ensure segregation of duties |  | 0 | 0 | bar: NOV WK 3
Storerooms’ operating hours are established in advance and department heads are to adhere to lead times on deliveries are established to minimize inventories |  | 0 | 0 | bar: NOV WK 3
|  | 0 | 0 | bar: NOV WK 3
COST CONTROL
Establish Internal Controls For Cost Controller To Ensure : |  | 0 | 0
- Control Of Food Cost |  | 0 | 0 | bar: DEC WK 3
- Control Of Beverage Cost |  | 0 | 0 | bar: DEC WK 3
- Control Minimum & Maximum Stock |  | 0 | 0 | bar: DEC WK 3
- Pricing Of Menus |  | 0 | 0 | bar: NOV WK 1
SOFTWARE SET UP
Opera |  | 0 | 0 | bar: NOV WK 2 to DEC WK 2
FBM |  | 0 | 0 | bar: NOV WK 2 to DEC WK 2
SUN / VISION |  | 0 | 0 | bar: NOV WK 2 to DEC WK 2
PAYROLL |  | 0 | 0 | bar: NOV WK 2 to DEC WK 2
MANNING
Financial Controller (Expat) |  | On Board
General Cashier/Paymaster (Expat)
Income Auditor (Local)
Accounts Receivable/Payable (Expat)
Cost Controller/ Store In Charge (Expat)
Store Keeper/ Receiving (Local)
Purchasing Manager (Expat)

## Front Office
FRONT OFFICE | DAYS LEFT | 84 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 60
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Human Resources
Manning Guide | FOM / DOO | 0 | 0 | bar: OCT WK 1
Recruitment Schedule | FOM/ HR | 0 | 0 | bar: OCT WK 1
Staff Uniforms Schedule | FOM / EHK | 0 | 0 | bar: OCT WK 2
Staff Rostering | FOM | 0 | 0 | bar: OCT WK 2
Creating Staff Personal Files | FOM | 0 | 0 | bar: OCT WK 2
FF&E & Stocks
FF&E list(Front Office and General Related) | FOM | 0 | 0 | bar: OCT WK 1
FF&E Schedule | FOM / Material | 0 | 0 | bar: OCT WK 1
Prepare Store Req list per Section | FOM | 0 | 0 | bar: OCT WK 2
Prepare Purchase Requests for Sections | FOM | 0 | 0 | bar: OCT WK 2
Room Configuration
Room Types and Descriptions | FOM / S&M | 0 | 0 | bar: OCT WK 1
Room Numbering | FOM / ENG | 0 | 0 | bar: OCT WK 1
Signage | FOM / ENG | 0 | 0 | bar: OCT WK 1
Product Knowledge
Services and Timings | FOM/F&B Mgr | 0 | 0 | bar: OCT WK 2
Other Dept.Services related to guests | FOM/ Other DH | 0 | 0 | bar: OCT WK 3
Food and Beverage Timings | GRO / F&B | 0 | 0 | bar: OCT WK 3
Front Office Handbook | GRO / FOM | 0 | 0 | bar: OCT WK 4
On-Site Activities | GRO | 0 | 0 | bar: OCT WK 3
Update Telephone Book in PMS | Ope / IT | 0 | 0 | bar: OCT WK 3
Off-Site Activities & Informations | Concierge / GRO | 0 | 0 | bar: OCT WK 3
Reservations
Receives Rate Structure | FOM / S&M | 0 | 0 | bar: OCT WK 2
Business on the Books | FOM/Revenue Mgr | 0 | 0 | bar: OCT WK 2
Receive Market Segment Manual | S&M | 0 | 0 | bar: OCT WK 3
Receive Business Mix Budget | FC | 0 | 0 | bar: OCT WK 3
Training on Electronic Procedure & System | FOM / REV | 0 | 0 | bar: NOV WK 3
Technical System Configuration
Email Accesses | IT | 0 | 0 | bar: NOV WK 1
PMS Set-Up | KIT / IT | 0 | 0 | bar: NOV WK 1
GDS-Set-Up | FOM / S&M | 0 | 0 | bar: OCT WK 1
Internet Access in Rooms & Public Areas | IT | 0 | 0 | bar: OCT WK 2
PABX Set-Up | IT / FOM | 0 | 0 | bar: OCT WK 4
Hotel web site set up | IT / FOM | 0 | 0 | bar: OCT WK 1
Computer/Printer Arrival & Set-Up Deadlines | IT / FOM | 0 | 0 | bar: OCT WK 1
Fax Machine & Copier Arrival Deadlines | FOM / Materials | 0 | 0 | bar: OCT WK 1
Public Area Tel Booth | IT / FOM | 0 | 0 | bar: OCT WK 1
Guest Room Telephones | IT / FOM | 0 | 0 | bar: OCT WK 2
Set-Up
Office Lay-Out | FOM / ENG | 0 | 0 | bar: OCT WK 1
Reception and Concierge Counter | FOM / ENG | 0 | 0 | bar: OCT WK 1
Other Public Areas Responsibilities | FOM / HK | 0 | 0 | bar: OCT WK 1
SwitchBoard Lay-Out | FOM | 0 | 0 | bar: OCT WK 1
Business Centre Layout | FOM | 0 | 0 | bar: OCT WK 1
Telephone Extensions | FOM / Tel Ope | 0 | 0 | bar: OCT WK 1
Valet Parking Desk | FOM | 0 | 0 | bar: OCT WK 2
Luggage Room | FOM | 0 | 0 | bar: OCT WK 1
Training
PMS Classroom Training | FOM / KIT / IT | 0 | 0 | bar: NOV WK 1
PMS Workplace Training | FOM / KIT | 0 | 0 | bar: NOV WK 1
Hotel Orientation | HR / FOM | 0 | 0 | bar: NOV WK 2
Frequent Flyer Training | FOM / S&M | 0 | 0 | bar: NOV WK 3
Product Knowledge Training | FOM / Section | 0 | 0 | bar: NOV WK 1
Communication Training | FOM / HR | 0 | 0 | bar: NOV WK 2
Policy Training | FOM | 0 | 0 | bar: NOV WK 3
Procedure SOP Training | FOM | 0 | 0 | bar: NOV WK 4
Telephone Standards and Use Training | N Manager | 0 | 0 | bar: NOV WK 4
Foreign Currency Training | ACC | 0 | 0 | bar: NOV WK 3
Guest Internet Training | IT | 0 | 0 | bar: NOV WK 2
Grooming Standards | HR | 0 | 0 | bar: NOV WK 1
Guest Safety Deposit Box Training | GRO / ACC | 0 | 0 | bar: NOV WK 3
Up Selling Training | FOM | 0 | 0 | bar: NOV WK 4
Departmental OJT | HR | 0 | 0 | bar: NOV WK 1
Emergency Procedures | ENG | 0 | 0 | bar: DEC WK 1
Room Rate and Room code Training | FOM | 0 | 0 | bar: DEC WK 1
Market Segment Training | FOM | 0 | 0 | bar: DEC WK 2
Reservation Call Sequence Training | FOM | 0 | 0 | bar: DEC WK 1 to DEC WK 2
System Shut-Down Training / Contingency Plan | IT / FOM | 0 | 0 | bar: DEC WK 1
Accounting
Cash Drop Safe | ACC | 0 | 0 | bar: DEC WK 1
Cashier Float Procedure | ACC | 0 | 0 | bar: DEC WK 2
General Cashier Procedure | ACC | 0 | 0 | bar: DEC WK 3
Lobby/House Phone Procedure | FOM / Tel Ope | 0 | 0 | bar: NOV WK 4
Barter Agreement List |  | 0 | 0 | bar: DEC WK 1
Credit List And Procedure | S&M | 0 | 0 | bar: DEC WK 2
Collaterals
Corporate In Room Collaterals | S&M | 0 | 0 | bar: NOV WK 4
Hotel Defined In Room Printing | HK | 0 | 0 | bar: NOV WK 3
Corprate FO Collaterals | FOM | 0 | 0 | bar: NOV WK 3
Guest Directory | S&M | 0 | 0 | bar: NOV WK 4
Transportation
Taxi Services | FOM | 0 | 0 | bar: DEC WK 1
Hotel Shutlle Bus Services | HR / FOM | 0 | 0 | bar: DEC WK 1
Hotel Airport Transportation Services | FOM | 0 | 0 | bar: DEC WK 1
Policies & Procedures
Prepare & Receive Internal Policies | FOM | 0 | 0 | bar: OCT WK 1
Prepare & Receive Internal Procedures SOP's | FOM | 0 | 0 | bar: OCT WK 1
Property Defined FO Services
Define Business Centre Timings | FOM | 0 | 0 | bar: OCT WK 4
Define Business Centre Services & Prices | FOM | 0 | 0 | bar: OCT WK 4
Define Concierge Services & Partner Agents | FOM | 0 | 0 | bar: OCT WK 4
Define VIP Amenities | FOM / F&B | 0 | 0 | bar: DEC WK 1

## Housekeeping
HOUSEEEPING | DAYS LEFT | 84 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 60
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
Orientation to the Project
Become familiar with Project/Property |  | 0 | 0 | bar: OCT WK 1
Become familiar with Owner/Owning Company |  | 0 | 0 | bar: OCT WK 1
Inventory all HK materials, manuals |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
Read and become familiar with all materials under HK |  | 0 | 0 | bar: OCT WK 1
Review preliminary manning guide with GM/HR |  | 0 | 0 | bar: OCT WK 1
Review the pre-opening budget |  | 0 | 0 | bar: OCT WK 1
Review the opening schedule |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Technical specifications /FF&E Managemnet
Curtains/Blackouts |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Accessories - Hair dyers/Kettles/bathroom scales/magnify mirrors |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
FF&E(Asset register)set up |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
FF&E deliveries/delivery note logs |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
FF&E hand over by main contractor/FF&E tags /logs |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
FF&E spares ( furniture) |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
Critical Path
Review the base critical path for the Hotel & HK |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Fine tune the base critical path for HK |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Personnel Management
Establish all areas and nos. of manning required/approved GM |  | 0 | 0 | bar: OCT WK 1
candidate profiles/Recruitmnet schedule |  | 0 | 0 | bar: OCT WK 3 to NOV WK 2
Establish Hiring Guide |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Departmnetal orientation |  | 0 | 0 | bar: NOV WK 1 to NOV WK 4
Conduct Skills training for all staff |  | 0 | 0 | bar: NOV WK 1 to DEC WK 4
Product knowledge / policy & procedure training lists / test. |  | 0 | 0 | bar: DEC WK 1 to DEC WK 4
Make Training Calender |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Make Training Manual |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Write Job Descriptions |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Draw initial training plan for HK staff & determine who can do training (HR, HK Spvs, Suppliers) |  | 0 | 0 | bar: OCT WK 1 to OCT WK 4
staff on board schedules |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Operation Management
Write standards manual (SOP) for total housekeeping & laundry operations |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Service procedures |  | 0 | 0 | bar: OCT WK 1 to OCT WK 3
Establish daily routine railroutes with checklists |  | 0 | 0 | bar: OCT WK 4 to NOV WK 2
Make Log Formats |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Make Job Allocation Formats |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Conduct Time and Motion Study |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Purchasing Orders /Par levels
Chemicals (check pre-opening budget) |  | 0 | 0 | bar: OCT WK 1
Cleaning material ( SOE) |  | 0 | 0 | bar: OCT WK 1
HK machinery |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Trolleys & hangers |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Approved & required guest amenities (bathroom & guest room lay out, printing & stationery |  | 0 | 0 | bar: OCT WK 1 to OCT WK 3
Linen orders ( HK / F&B) /Par levels |  | 0 | 0 | bar: OCT WK 1 to OCT WK 3
Guest amenities/stationeries& colleterals/Non wowen items |  | 0 | 0 | bar: OCT WK 1 to OCT WK 3
Implement opening inventories and follow up inventories |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Implement bathroom / room set up |  | 0 | 0 | bar: DEC WK 1 to DEC WK 3
Coordination with other departments
Set up standards for future laundry/uniform operations. Collection days/ hours, pick up days/hours for all |  | 0 | 0 | bar: OCT WK 4
Advice other departmnet on Standards & procedures HSK & laundry dept. |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Hours & days of pick up clean & delivery of dirty -location for uniforms & linen |  | 0 | 0 | bar: OCT WK 4
Trolleys available for rooms / F&B - locations |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Uniforms - approved style on uniforms |  | 0 | 0 | bar: OCT WK 1 to OCT WK 2
Procedures for uniform issue and repairs. |  | 0 | 0 | bar: OCT WK 3
Laundry / Linen Room
Commsion areas to be undertaken for operation for HSK & laundry equip setting up & snagging |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Establish all input required for Laundry Micros |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Technical control & quality control check lists |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Washing machines, dryers, ironing for laundry area before first use. Report defaults |  | 0 | 0 | bar: DEC WK 4
Establish Procedures Delivery & collection of linen |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Agree first delivery date of stock in time for training |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Linen control
Agree system of linen control with Financial Controller |  | 0 | 0 | bar: NOV WK 1
Implement opening inventories & follow up inventory policy & procedures |  | 0 | 0 | bar: NOV WK 1
Prepare discard linen recycling procedures |  | 0 | 0 | bar: NOV WK 1
Linen arrives on site |  | 0 | 0 | bar: DEC WK 1
Pre-washing of linen |  | 0 | 0 | bar: DEC WK 2
Secure storage and report deviation from standards. |  | 0 | 0 | bar: NOV WK 4
Policy & procedures of issuance, circualtion, misuse control |  | 0 | 0 | bar: NOV WK 4
Uniform schedule
Uniforms - approved style on uniforms |  | 0 | 0 | bar: OCT WK 4
Pre opening T-Shirts |  | 0 | 0 | bar: OCT WK 4
Total manning list for uniforms/ confirm with HOD;s |  | 0 | 0 | bar: OCT WK 4
Produce & issue uniform schedule per dept. (seamstress to be available for small alterations minimum 2 weeks prior to opening) |  | 0 | 0 | bar: OCT WK 4
Messurment sessions schedule |  | 0 | 0 | bar: DEC WK 1; DEC WK 4
Fitton schedules and Dilivery |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Storage
Linen |  | 0 | 0 | bar: NOV WK 1
Uniforms |  | 0 | 0 | bar: NOV WK 1
Cleaning supplies |  | 0 | 0 | bar: NOV WK 1
Machinery & trolleys |  | 0 | 0 | bar: NOV WK 1
Storage areas policy & procedures |  | 0 | 0 | bar: NOV WK 1
Cleaning materials are on site |  | 0 | 0 | bar: OCT WK 2
Daily follow up of recycled & non-recycled inventory items deliveries |  | 0 | 0 | bar: NOV WK 1 to NOV WK 4
Amenities and HK Supplies |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Take out / Stores P&P |  | 0 | 0 | bar: DEC WK 2 to DEC WK 3
Offices and Stores Set Up
HK Offices |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Lost and Found Stores |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Housekeeping Supplies Store |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Chemical Room |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Guest Loan Items Store |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Equipment Store |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Floor Pantry |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Linen Store |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Uniform Room |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Outside Contracts
Finalize: Window cleaning |  | 0 | 0 | bar: NOV WK 1
Plant & Flower suppliers |  | 0 | 0 | bar: NOV WK 1
Outdoor Cleaning |  | 0 | 0 | bar: NOV WK 1
Carpet Maintenance |  | 0 | 0 | bar: NOV WK 1
Marble Maintenance |  | 0 | 0 | bar: NOV WK 1
Make Service procedure outline |  | 0 | 0 | bar: NOV WK 1
Pest Control Hotel |  | 0 | 0 | bar: NOV WK 1
Fragrance contractors |  | 0 | 0 | bar: NOV WK 1
Garbage Procedure
Familiarized w/ garbage collection area & system garbage concept incl. Environmental strategy |  | 0 | 0 | bar: DEC WK 4
Liaise with garbage collection companies |  | 0 | 0 | bar: DEC WK 4
Hygiene & Pest Control
Establish pest control procedures (local contractor) |  | 0 | 0 | bar: OCT WK 3
Request quotations for service agreement to include no. of deep cleans and requested results, call out for vermin infestations |  | 0 | 0 | bar: OCT WK 3
Handover from Building Contractor
Mock Up room Set up & Review |  | 0 | 0 | bar: OCT WK 2
Receive items from fit out contractor |  | 0 | 0 | bar: NOV WK 4
Snag Mock up room |  | 0 | 0 | bar: OCT WK 3
Hotel Snag Phase I |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Hotel Snag Phase II |  | 0 | 0 | bar: DEC WK 2 to DEC WK 3
Take Over final list with snags not completed |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Agree handover schedule for rooms and public areas |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Arrange for post-construction deep cleaning |  | 0 | 0 | bar: DEC WK 1 to DEC WK 4
Housekeeping Trial Runs
Coordinate the trial run programme with opening schedule |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Identify and agree trial run procedures for Rooms |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Publish trial run schedules |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Begin trial runs |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Assist in monitoring trial runs and feedback sessions |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4

## Purchasing
PURCHASING | DAYS LEFT | 84 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 60
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
General
Submit OS&E proposal |  | 0 | 0 | bar: OCT WK 4 to NOV WK 2
Fire Evacuation Plan |  | 0 | 0 | bar: NOV WK 2 to NOV WK 4
LCD Television |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Walkie Talkies |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Room Safe Boxes |  | 0 | 0 | bar: DEC WK 1 to DEC WK 4
Room Minibar |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Hotel Internal Signs |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Staff Accommodation Items |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Engineering
Engineering Tools |  | 0 | 0 | bar: NOV WK 1 to NOV WK 4
Food & Beverage
Banquet equipments, chinaware, cutleries, glassware and utensils |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Wine Bar Equipments |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Kitchen Display Items |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Kitchen Utensils |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Stewarding Items |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Housekeeping
Cleaning Equipments |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Cleaning Chemicals and Materials |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Guest Room Amenities |  | 0 | 0 | bar: DEC WK 3 to JAN WK 1
Room Linen |  | 0 | 0 | bar: DEC WK 3 to JAN WK 1
Bathroom Linen |  | 0 | 0 | bar: DEC WK 3 to JAN WK 1
Guest Room Bed and Mattress |  | 0 | 0 | bar: DEC WK 3 to JAN WK 1
Trolleys for HK |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Out door and Indoor Plants contract |  | 0 | 0 | bar: OCT WK 3 to OCT WK 4
Front Office
Flags and Flag Poles 8mtr 12 mtr 5x3 6x4 |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
General
Catering Company |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Soft drink proposal |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Transportations' For Staff |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Laundry Service |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
HACCP Certification TUV SGS BUREAU VERITAS |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
External cleaning for Building |  | 0 | 0 | bar: NOV WK 3 to DEC WK 1
Outside Catering Van |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Fire Retardent Safes |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Beverage Contract |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Contract for vegetables |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1
Contract for Bread Items |  | 0 | 0 | bar: NOV WK 4 to DEC WK 1

## Engineering
ENGINEERING | DAYS LEFT | 84
| Working days left | 60
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
General
Set up Engineering files |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
Complete Emergency Manual |  | 0 | 0 | bar: NOV WK 3 to DEC WK 1
Complete Maintence Manuals / S.O.P.s/ Vol (1) To (5) |  | 0 | 0 | bar: NOV WK 3 to DEC WK 1
Job Descriptions |  | 0 | 0 | bar: OCT WK 4 to NOV WK 1
Complete R&M Budgets |  | 0 | 0 | bar: OCT WK 4 to NOV WK 2
Complete Energy Budget |  | 0 | 0 | bar: OCT WK 4 to NOV WK 2
Fire Plans for Back of Guest Room Doors |  | 0 | 0 | bar: OCT WK 4 to DEC WK 2
Master Key System |  | 0 | 0 | bar: OCT WK 4 to DEC WK 2
Walkie Talkies |  | 0 | 0 | bar: NOV WK 1 to DEC WK 2
Fire Cabinets & Suits for Fire Fighters |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Finalise Key Policy |  | 0 | 0 | bar: NOV WK 4 to DEC WK 2
Recruitment |  | 0 | 0 | bar: OCT WK 1 to NOV WK 4
Prepare Snagging List |  | 0 | 0 | bar: OCT WK 4 to NOV WK 4
Prepare Testing & Commissioning Check Lists For M.E.P. |  | 0 | 0 | bar: NOV WK 1 to DEC WK 2
Obtain Quotes For Annual Maintenance Contract |  | 0 | 0
Engineering Tools |  | 0 | 0 | bar: OCT WK 3 to NOV WK 3; DEC WK 2 to DEC WK 4
Engineering Forms |  | 0 | 0 | bar: NOV WK 1 to NOV WK 3
Finalise Mock Rooms |  | 0 | 0 | bar: OCT WK 1 to OCT WK 3
SAT/TV System |  | 0 | 0 | bar: NOV WK 2 to DEC WK 1
Kitchen Walkin Freezers |  | 0 | 0 | bar: OCT WK 3 to NOV WK 2
General Stores /Shelving |  | 0 | 0 | bar: NOV WK 1 to NOV WK 3
Lobby Reception Desk/set up computer terminals etc |  | 0 | 0 | bar: NOV WK 2 to NOV WK 3
Lobby Café Counter |  | 0 | 0 | bar: NOV WK 2 to NOV WK 4
Take Over Engineering Workshop |  | 0 | 0 | bar: NOV WK 3 to DEC WK 2
Preventative Maintenance Check List/and all work orders |  | 0 | 0 | bar: NOV WK 2 to DEC WK 1
Engineering/Training |  | 0 | 0 | bar: NOV WK 3 to DEC WK 4
Testing Of All M.E.P. Equipment |  | 0 | 0 | bar: NOV WK 4 to DEC WK 4

## IT
I.T. DEPARTMENT | DAYS LEFT | 84 |  | 0 | 25 | 50 | 75 | 90 | DONE
| Working days left | 60
ACTIONS | ACTION BY | DONE / STATUS |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | JAN
|  |  |  | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4 | WK 1 | WK 2 | WK 3 | WK 4
General
Systems configuration |  | 0 | 0
Location and layout of EDP office and computer room |  | 0 | 0
Adequacy of alarm systems, fire fighting equipment, aircon, power stabilisers, surge protectors, |  | 0 | 0
lightning protection system |  | 0 | 0
Cabling requirements |  | 0 | 0
Back-up operations and emergency procedures |  | 0 | 0
Hardware and software agreements |  | 0 | 0
Adequacy of front office and F&B physical locations |  | 0 | 0
Layout of stations to allow sufficient space for monitors, printers, cash registers, credit card machines, cables, etc |  | 0 | 0
Provision of special electrical outlets for terminals, etc. |  | 0 | 0
Develop a systems emergency plan |  | 0 | 0
Test all systems including the emergency plan |  | 0 | 0
INTER-DEPT, ACCOUNTING RELATED FUNCTIONS |  | 0 | 0
Installation
Network Cabling to be completed in Data Center |  | 0 | 0 | bar: OCT WK 3 to NOV WK 2
Network Cabling to be completed in in all IDF Rooms |  | 0 | 0 | bar: OCT WK 4 to NOV WK 3
Network Cabling to be completed in all admin Office's |  | 0 | 0 | bar: OCT WK 4 to NOV WK 2
CC TV Project completion and testing |  | 0 | 0 | bar: DEC WK 1 to DEC WK 3
IP Telephone Project completion and testing |  | 0 | 0 | bar: DEC WK 2 to DEC WK 3
HSIA System installation and testing |  | 0 | 0 | bar: DEC WK 2 to DEC WK 3
Apply for telephone lines - Telecommunication |  | 0 | 0 | bar: OCT WK 3
Ordering the Servers , Desktops,Printers, Scanners,etc., |  | 0 | 0 | bar: OCT WK 1
Applying the Internet line connection from ISP |  | 0 | 0 | bar: OCT WK 3
Data Center to be ready |  | 0 | 0 | bar: OCT WK 4 to NOV WK 4
Opera PMS installation, testing and training for users |  | 0 | 0 | bar: DEC WK 2 to JAN WK 1
Micros POS installation, testing and training for users |  | 0 | 0 | bar: DEC WK 2 to JAN WK 1
HR & PayRoll System installation, testing and training for users |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Backoffice System installation ,testing and training for users |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Call Accouting System installation and testing |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Key Card system installation and testing |  | 0 | 0 | bar: DEC WK 1 to DEC WK 2
All interfaces testing and commissioning |  | 0 | 0 | bar: DEC WK 4 to JAN WK 1
Antivirus system installation and testing |  | 0 | 0 | bar: DEC WK 3 to DEC WK 4
Backup System installation and testing |  | 0 | 0 | bar: DEC WK 4 to JAN WK 1
PC , Scanner and printer distribution in concerned department |  | 0 | 0 | bar: DEC WK 4 to JAN WK 1
Micros Workstation distribution in the Revenue Center |  | 0 | 0 | bar: DEC WK 4 to JAN WK 1
Make sure all the systems and interface are working for the soft opening |  | 0 | 0 | bar: JAN WK 1
Appoint IT Staff's and Training |  | 0 | 0 | bar: NOV WK 1 to NOV WK 2
Soft Opening |  | 0 | 0 | bar: JAN WK 1